CDS Family & Behavioral Health Services, Inc.

Accessibility Plan

Five Year Plan

Year Three
September, 2008- August 2009

Submitted to
Jim Pearce

Monday, August, 2008

Prepared by
Peggy Vickers

Quality Assurance Coordinator
Accessibility Work Group

This publication can be made available in multiple media formats upon request.

# CDS

Executive Summary

| ## Mission Strengthening Communities by Building Strong Families. # Accessibility Plan |  |  |
| --- | --- | --- |
|  | Geographical Area: Alachua, Baker, Bradford, Columbia, Dixie, Gilchrist, Hamilton, Lafayette, Levy, Madision, Putnam, Suwannee, Taylor and Union Counties |  |
|  | CDS 1300 NW 6th Street GAINESVILLE, FL 32601 (352) 334-3800 |  |

CDS is a not for profit community based agency dedicated to providing quality, affordable children and youth and behavioral health services in partnership with our communities.  CDS became incorporated March 20, 1970.  Interface Youth Shelter opened in Alachua County in 1978 as one of the first runaway shelters in the State of Florida.  CDS still remains today, a provider of specialized services and programs for truant, runaway, homeless, ungovernable and lockout/throwaway youth and their families. CDS also provides substance abuse and mental health prevention, outreach, intervention and outpatient services for youth and adults.

- CDS believes services should be readily accessible to the people we serve.

  - In order to meet the needs of our communities our residential shelter programs are accessible 24 hours a day, seven days a week.

  - Our 1-800 # is answered by residential staffs that are able to conduct an initial screenings, provide phone counseling, and make appropriate referrals for services 24 hours a day, 7 days per week.

  - Many of our programs operate outside of “normal business hours” in order to meet the needs of those persons who work or go to school.  Many of our services are school-based or site based.

  - CDS has worked diligently to ensure that service locations are within a 60-minute drive for all persons served.

- CDS believes services should be delivered in a respectful and culturally competent manner.

- CDS believes that its staff should, to the extent possible, be representative of the communities served.  CDS works diligently to provide participants access to a diverse and culturally competent staff in all of our programs.

- CDS believes that prevention and intervention services for at risk children and youth, and adults are a right, not a privilege, and that families and other individuals in need should be able to access appropriate services regardless of their ability to pay. As such, CDS has various methods to receive compensation for services:

  - Federal, State and TANF funds

  - Other grant funds

  - Sliding Fee Scale (and options to reduce fees, with supervisor’s approval)

  - Limited access to student interns

  - Targeted donations

  - Referrals to other agencies

- CDS believes that services should be delivered in an environment that meets the needs of the persons served, including:

  - ADA compliance

  - Safety and security

  - Adequate privacy

- CDS believes that its duty is to assist in removing barriers that prevent a person served from fully integrating into the community of his/her choice.  Therefore, CDS provides:

  - Outreach services and education through community programs and its web site

  - A place to host community coalition meetings and provide community education forums

  - A place to host support groups

This Accessibility Plan outlines the methodology by which we have identified barriers within CDS, our plans for removal of such barriers, our ongoing commitment to accessibility planning, and how we will communicate this plan to the public.

CDS is committed to providing a barrier-free environment for our participants, their families, our volunteers, staff, guests and the community. CDS has established an Accessibility Work Group (AWG) committed to accessibility planning, and will continue to work with our community partners towards a barrier-free society.

1. Aim - The aim of the Accessibility Work Group (AWG) for CDS is to provide a barrier free environment for our participants, their families, our volunteers, staff, and guests of CDS. The AWG will ensure compliance with American Disabilities Act (ADA) as a minimum standard, will publish an annual Accessibility Plan, and recommit annually to accessibility planning and to broadening our scope for the removal and prevention of barriers.

2. CDS commitment to accessibility planning - CDS provides counseling services that support participation in all areas of life for children, youth and adults with behavioral health needs. We focus on the strengths of individuals and their families at home, school, workplace, and community. We pursue research on best practices, education and advocacy, and participate in local, regional and state wide system of services. CDS is committed to providing a barrier-free environment for our participants, their families, our volunteers, staff and guests; to broadening the scope of accessibility planning; and to continue working with our community partners to achieve a barrier-free society.

3.  Description of CDS - CDS provides services to 14 counties: Alachua, Baker, Bradford, Columbia, Dixie, Gilchrist, Hamilton, Lafayette, Levy, Madision, Putnam, Suwannee, Taylor and Union counties and three judicial circuits. CDS maintains facilities in the three largest counties, with prevention, intervention and residential shelter programs in Alachua, Putnam and Columbia counties. The geographical area is mostly economically poor and rural, spanning from North Central Florida to the southern border of Georgia. CDS offers a variety of programs and services such as, but not limited, to screening, assessment and an intervention individual plan, group, family and individual counseling to meet the needs of participants in our program.

CDS has applied for a survey with the Commission on Accreditation of Rehabilitation Facilities (CARF) during FY 2008-2009.  A site visit is anticipated in October or November of 2008.  CDS maintains Substance Abuse Licenses in Alachua, Putnam and Levy Counties, and Child Caring Licenses for Interface-Central, Interface-Northwest and Interface-East.    CDS has met or exceeded all performance measures in the CINS/FINS, SAMH and PFSF for fiscal year 2007-2008 contract. Major Funders includes: Partnership for Strong Families & Community Partnership for Children (contracted through Florida Department of Children and Families) and Circuit 3, 8 and 7 SAMH Program Offices with the Department of Children and Families, Florida Network of Youth and Family Services (funded through Florida Department of Juvenile Justice) and United Way.

The organization has an annual operating budget of approximately $5.4 million, approximately 135 full and part-time employees and is a multi-program agency administered through a central office.  CDS programs are:

Non-Residential Services:	Substance abuse prevention, intervention, and outpatient treatment programs for youth and adults. Mental Health Case Managers and outreach services for TANF youth and adults.

Prevention Services:	Youth delinquency prevention and substance abuse prevention programs for youth and adults

Alpha:		Prevention/Intervention Day Program.

Beta:			Prevention/Intervention Day Program.

TASC:	Substance abuse and mental health assessment services for youth involved with the Juvenile Justice System.

Independent Living:	Life skills for foster care and other eligible youth.

Interface/Family Action:	Program for runaway, truant and ungovernable youth and families in crisis.

Each of these programs has distinct goals and activities, which are consistent with the organization's mission.

For purpose of administration CDS utilizes centralized fiscal, human resources and data systems to enhance program management.

4. Objectives for this Accessibility Plan:

a) Identifies the membership of the Accessibility Work Group.
b) Describes the process and methodology by which CDS will identify barriers.
c) Identify the goals set by the Accessibility Work Group by fiscal year and outcome achieved.

d) Identify barriers that have been successfully removed in the past year.
d) Describes the barriers that are to be removed in upcoming years.
e) Describes how CDS will communicate this accessibility plan to the public.

a)  Accessibility Work Group - In consultation with the Board of Directors, the CDS CEO established the AWG in FY 2005/2006 and authorized the group to pursue its stated aim and objective. The CEO as coordinator of the Accessibility Work Group (AWG) appointed Peggy Vickers, Quality Assurance Coordinator as chair of the group.

Membership -The following members form the AWG steering committee:

| Member | Program Area |
| --- | --- |
| Sam Clark | Chief Operations Officer |
| Peggy Vickers | Quality Assurance Coordinator |
| Herman Miller | Maintenance Supervisor |

b)  Barrier-Identification Methodologies - The AWG may use one or a combination of the following methods to identify, remove, and prevent barriers:

| Method | Description |
| --- | --- |
| Identified Barriers | Review and incorporate into the plan any barriers as identified by participants, their families, volunteers, staff, guests, monitoring or licensing bodies. |
| Conduct surveys | Survey participants, their families, volunteers, staff and community partners to identify barriers and present suggestions for resolutions. |
| Conduct focus groups | Hold focus group sessions with staff and volunteers and with various participants to obtain their expertise. |
| Consult community groups and organizations | Consult community organizations to educate the committee and staff such as the Center for Independence, Vocational Rehabilitation, University of Florida Counseling Rehabilitation Program, and Blind Services. |
| Conduct accessibility audit | Perform a review and audit utilizing available audit tools, such as the CARF Guide to Accessibility. |
| Consult professional services | Enlist professional services where appropriate, in matters such as architectural design, computers and business equipment, sensitivity training. |

c) Goals for Identifying Barriers by Fiscal Year and Outcome

FY 2005-2006:  1.  Complete a physical, communication and attitudinal accessibility assessment of all CDS sites.  2.  Within fiscal budget correct deficiencies noted from the assessment.  3. Apply for available funding to renovate IYP-E.  4. Board charged the Resource Development with changing the name, logo and web site address to make the corporation more accessible for children and youth services.

AWG began by establishing a baseline in FY 2005 -2006.  The AWG used several of the methods noted above to gather information and identify existing barriers within CDS facilities. Accessibility audits were conducted along with staff interviews and consultation with professional services for the 1218 and 1300 and 3615 buildings, IYP-NW and IYP-Central and IYP-East, which provided valuable input into this identification process. The committee also participated in the research of the corporate name change etc.

FY 2006-2007:  1.  Develop an agency wide Accessibility Plan.   2. Change the agency name.  3.  Begin using people first language throughout the agency.  4. Train agency personnel on the person centered approach accentuated by beginning to refer to persons served as participants as opposed to clients.  4. Begin the process of changing all policies and procedures to reflect name change and references to client.  5. Contract with building contractor to make renovations to IYP-E.  6. Expand the Accessibility Plan to include all of the following: physical, attitudinal, information, communication and technology.

During FY 2006-2007, the AWG used the feedback from legal consultants, our insurance company, quality assurance reviews and continued to use the information gathered in FY 2005-2006 Accessibility Audits.  The Board of Directors officially changed the corporation name on 1/07.

FY 2007-2008:  1. Continue the process of changing all policies and procedures and documents to reflect the name change and reference to participant.  2. Correct accessibility deficiencies within available funding.  3.  Expand staff input into the Accessibility Plan by adding questions to staff retreats in preparation for the Strategic Plan.  4.  Research funding sources for renovations for the 1300 Building.  5.  Expand the Accessibility Plan to include physical, attitudinal, information, communication, technology, employment, environmental and financial.

During FY 2007-2008, the AWG used the feedback collected from stakeholders, employee surveys, participant satisfaction forms, CARF consultant’s review as well as lessons learned from previous years.

FY 2008-2009:  1.  Using the Accessibility Plan verify corrections have been maintained and prioritize IYP-NW and IYP-C corrections.  2.  Apply for foundation funds for the 1300 Building for renovations. 3 Assess current Accessibility Plan to ensure it include physical, attitudinal, information, communication, and technology, employment, environmental and financial.

FY 2008-2009, the AWG is in the process of collecting information about accessibility issues from Coordinators and their staff during this years staff retreats.  There is also a plan to re-assess findings from the original Accessibility Audits.

FY 07-08 an inventory of existing barriers was established and divided into the following categories:

- Architectural and Physical – All three IYP Shelter Programs and 3615 Building now meet ADA requirements.  The 1218 and 1300 buildings were constructed and occupied by the agency prior to the passage of the ADA requirements.  CDS continues to seek funding for upgrades to the 1300 building.

- Attitudinal – CDS continues to seek to reduce the stigma attached with persons who runaway and homeless youth and persons with substance abuse and mental health problems.

- Environmental – CDS strives to create an environment where people are comfortable and feel their confidentiality is maintained.  Additional effort is needed to create environments that are reflective of the cultural customs of the participants we serve.

- Employment – CDS strives to maintain a diverse workforce sensitive to the unique needs of our participants.  CDS continues to strive towards hiring and maintaining the highest quality employees available.  The increase in Youth Care Workers hourly wage to $10.50 an hour has greatly reduced turn over.  Adjustments were made to the salaries of professional counseling staff has also assisted in stabilizing this workforce.

- Financial – CDS continues to offer a number of services without charge to children and youth, however it is time to re-evaluate the agency position or practices to continue to offer services without charge for participants that are costing the agency money, such as urinalysis testing.  Upgrades to IYP-E were funded through the Department of Children Youth and Families for homeless shelters.  Upgrades to Fiscal software was funded by the?  The agency was awarded from the from the Department of Health and Human Services, Administration for Children and Families Office of Community Services, Compassion Capital Funds targeting Capacity Building Programs funded Human Resources and Resource Development soft ware, computer laptops for staff and staff training.  A grant funded from SED-Net also funded training materials for participants.  Additionally, a total of six Family Action Counselors and 1.5 Outpatient Services FTE positions were cut due to funding reductions.

- Information, Communication and Technology - Some barriers were noted in how we share information with our participants, families and the community, and how we best utilize available technology to share such information.  In January 2007, Corner Drug Store changed its name to CDS Family & Behavioral Health Services, Inc. to better represent the type of services provided.  The response from our stakeholders was positive however, we continue to struggle with being recognized by our new name.  Our name continues to be a barrier in the area of communication and recognition.

- Policy, Practice and Procedures - Improvements to our policies and practices are ongoing, to ensure they reflect the underlying values of CDS and our commitment to a Person-Centered Care Model. Person-Centered Care is a philosophy of support and an attitude that focuses on the strengths, needs, abilities and preferences of individuals that recognizes the role and support of family, and promotes individualized choices by participants and their families.

- Transportation – CDS will provide services in areas where public transportation is available and offer services in schools and at sites where our participants are available.  Shelters continue to provide transportation to and from school as needed.

- Refer to Appendix A, Barrier Identification, for the list of identified barriers and the recommended action for removal.

d)  Recent Barrier-Removal Initiatives - Refer to Appendix A, Barrier Identification, for a list of identified barriers, and highlights of achievements for this past year. Dated items in the Completion Date column represent items successfully completed.

e)  Barriers To Be Addressed In The Upcoming Year - The removal of identified barriers is prioritized annually and presented to the CDS Executive Management Team for review, approval, and endorsement. The priority for removing barriers shall be determined on the basis of meeting the physical needs of our participants and the community, ensuring health and safety, and promoting barrier-free access to information. Refer to Appendix A, Barrier Identification, for a list of identified barriers, and their timeline for removal.

f)  Review and monitoring process - The AWG steering committee will commit to meeting every six months to:

- Continue to identify barriers

- Determine appropriate measures to ensure that removal of identified barriers has been achieved

- Ensure that all polices, practices, and services continue to prevent barriers

- Promote education and awareness

The AWG will recommit annually to the accessibility planning process, and will report annually to the CDS Executive Management Team.

g) Communication of the Plan - This Plan will be posted on our website, and is available in multiple media formats based upon request. Availability of this plan will be publicized to our participants, families, volunteers and employees in our publications and our Annual Report.

Appendix A:  Year Three Review of the Five Year Accessibility Plan

The following serves as CDS Family & Behavioral Health Services, Inc.’s Accessibility Plan for  five years, a new plan will be due FY 2011-2012. The purpose of this document is to provide a means to facilitate continual quality improvement in the area of accessibility.

CDS Family & Behavioral Health Services, Inc. is committed to providing an organizational milieu that seeks to accommodate the needs of all persons served, employees, volunteers and stakeholders. Central to this commitment is the removal of architectural, attitudinal, employment, and other barriers that may impede full access to the services and programs of the organization.

This Accessibility Plan corresponds to CDS Family & Behavioral Health Services, Inc. internal evaluation of barriers through the use of facility inspections, assessments of need, and consumer, stakeholder, and employee feedback. The Accessibility Plan is reviewed and updated on an annual basis as apart of the agency’s Strategic Planning process, reviewed and endorsed by Executive Management Team and CEO.

## Architectural Barriers

Goal: To help identify and minimize any architectural/physical barriers to the site(s).

Objective:

- Reassess by 9/30/08 IYP-C, IYP-NW and Outpatient Services using the Architectural Barriers identified in the Accessibility Plan.

- By 07/09 prioritize IYP-C, IYP-NW Shelters and Outpatient Services deficiencies for corrections based on the availability of funds.

- By 10/08 apply for funding for renovation costs for Outpatient Services.

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 3615 SW 13th St Gainesville, Fl 32608 | Improve accessible parking. | Fix accessible parking space (96 inch wide for the vehicle plus a 60 in wide striped access aisle adjacent to the parking space by repainting handicap parking space in front of Suite 1. | Maintenance Supervisor | 01/31/07 | 11/30/07 | Repainted parking space in front of Suite 1. Purchased stencil for handicap sign and white and blue paint, also repainted other handicapped parking lines in parking lot |
| 3615 SW 13th St Gainesville, Fl 32608 | Improve accessible parking. | Add van accessibility sign in front of Suite 7 space. | Maintenance Supervisor | 01/31/07 | 11/30/07 | Purchased signs on line. |
| 3615 SW 13th St Gainesville, Fl 32608 | Uneven surface next to proposed accessible parking spot. | Make I Make improvements to the parking lot by smoothing surface next to the first parking spot nearest Suite 2. | Maintenance Supervisor | 01/31/08 | 11/30/07 Deleted but was able to complete Spring of 2008 | Completed, contracted to redo the side walk. |
| 3615 SW 13th St Gainesville, Fl 32608 | Reviewed parking lot for uneven surfaces in the parking lot. | Make improvements to the parking lot by smoothing surface. | Maintenance Supervisor | On-going task. | 2008 | Completed, All depressions in the parking lot were filled in with asphalt. |
| 3615 SW 13th St Gainesville, Fl 32608 | No pedestrian ramp from parking lot. | A Request a professional assessment for ramp and request improvements based on results. | Maintenance Supervisor | 01/31/07 | 11/30/07 Deleted but was able to complete Spring of 2008 | Contracted to create ramp for accessible parking spot. |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 3615 SW 13th St Gainesville, Fl 32608 | Add accessible parking. | Create a new handicap accessible space in front of Suite 2. Designate space with a sign bearing the international symbol of van accessibility. | Maintenance Supervisor | 01/31/07 | Completed Spring of 2008 | Completed after ramp was finished. Purchased necessary supplies to complete. |
| 3615 SW 13th St Gainesville, Fl 32608 | No entrance is designated as handicap accessible. | Design a means to enter Suite 2 by notifying the receptionist in Suite 4. For example a doorbell. | Maintenance Supervisor | 01/31/07 | 1/07 08/08 | Completed added a door bell and a sign. Replace the sign. |
| 3615 SW 13th St Gainesville, Fl 32608 | No entrance is designated as handicap accessible. | Add smooth surface on both sides of the door. Stop the flow of water under the door. sto | Maintenance Supervisor | 01/31/07 | Completed Spring of 2008 Completed 11/15/06 | Designated Suite 2 door entrance and added a concrete pad by the door. |
| 3615 SW 13th St Gainesville, Fl 32608 | No doormats at the main entrances. | Purchase mat for Suite 2 and 4 entrances. | Maintenance Supervisor | 01/31/07 | 11/07 | Purchased from Sam’s |
| 3615 SW 13th St Gainesville, Fl 32608 | Missing signage for visually impaired. | Add brail entrance and exit signs. | Maintenance Supervisor | 08/31/08 | 03/30/08 Attempted to purchase sign at local Home Repair Companies. Need to order on line. |  |
| 3615 SW 13th St Gainesville, Fl 32608 | Fire doors must remain unlocked when employees are present. | Purchase bars for the fire exit doors. | Maintenance Supervisor | 10/30/06 | Worked on 10/21/06 Completed 12/30/06 Continue to monitor during fire drills. | Added guards to doors in Suite 1, 2, and 3. Suite 4 is kept open as main entrance. |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 3615 SW 13th St Gainesville, Fl 32608 | No designated accessible restroom. | Designate Suite 3 restrooms for handicap. Install a lever-type door handle or retrofit level on the existing doorknob. Add waterless soap dispenser no higher than 48 inches to male and female restrooms in Suite 3. Lower mirrors to 40 inches. Add height of 1-3 inches on the female toilet seat. | Maintenance Supervisor | 01/31/07 | 12/06 | Corrected all deficits. |
| 3615 SW 13th St Gainesville, Fl 32608 | Debris on sidewalks and parking lot. | Develop lawn maintenance on-going tasks to help keep facility accessible. For example keep sidewalks clean, keep plants and brush at least four inches away from the sidewalk. Power spray and blow off sidewalks and parking lot. | Maintenance Supervisor | 01/31/07 Change to on-going task. | On-going. | Hired a second Maintenance Person to assist with tasks. |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 3615 SW 13th St Gainesville, Fl 32608 | Communication Public telephone in lobby is not accessible. | Evaluate the cost of providing a public phone that is hearing aid or volume controlled, equipped with TDD or compatible. Review annual budget for upgrading telephone equipment | Quality Assurance Coordinator | On going review | 07/08 Completed | The agency’s new cell phones are equipped with the capability to text message. This mechanism has enhanced our communication with hearing impaired participants. |
| 3615 SW 13th St Gainesville, Fl 32608 | Doors exiting Suite 1 and 3 stuck when exiting the building. | Improve access to Suite 1 and 3. | Maintenance Supervisor and COO | On-going review during fire drills | 2007 2008 | Scraped the concrete to level it off for better access. Removed and replaced concrete to level the entrance to doors in Suite 1 and 3. |
| 3615 SW 13th St Gainesville, Fl 32608 | Outside lighting dim in parking lot after dark per employee feedback. | Assess parking lot lighting. | Maintenance Supervisor and CEO | 2008 | Outside lighting was reviewed and repaired. | Replaced bulb in large street light in the parking lot and repaired motion detector light on Suite 2 entrance. |
| 3615 SW 13th St Gainesville, Fl 32608 | Accessibility to evening appointments after building break-ins. | Assess cost of alarm system, security fence and other safety measures | Quality Assurance Coordinator, Building Committee, COO, and CEO | 2006 | 2006 | Installed security alarm, security fence and provided staff training on security measures. |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | Accessible parking space needs to be updated. | Add a van accessible sign to the international symbol of accessibility. | Maintenance Supervisor | 12/30/06 | Completed and checked on-going |  |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | Accessible parking space needs to be updated. | Add a passenger loading zone accessibility. Add a pedestrian aisle parallel to where vehicles pull up. Add a pedestrian aisle at least five feet wide and 20 feet long. Create a stable and slip resistant pedestrian aisle. Recommend using two parking spaces to create the handicap accessible space. | Maintenance Supervisor | 12/30/09 |  |  |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | Slope of the ramp is greater than 1:12. | Smooth out cracks on the slope. | Maintenance Supervisor | 12/30/08 |  |  |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | Improve outdoor access-entrance. | Add a door handle that is easy to operate with one hand that is not higher than 48 inches above the floor. Evaluate the need to replace the door with one that can be opened with a five pound or less of pressure. | Maintenance Supervisor | 12/30/06 | Completed | Consultation with the HR attorney indicated that the agency occupied this building prior to the enactment of the American Disabilities Act. Therefore the agency is not responsible for compliance at this time. |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | The second floor is not accessible. | Provide reasonable accommodations for anyone needing access to services. | Program Coordinator/COO | On going | On-going | See above. |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | Public restrooms and spaces are not accessible. | Add signs to adequately describe permanent rooms and spaces such as bathrooms and exits. (Braille signs should be mounted 60 inches high adjacent to the latch side of the door.) | Maintenance Supervisor | 12/30/06 | Completed | By 9/30/08 Check signage. |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | Public telephone in lobby is not accessible. Cell phones with text messaging are available for hearing impaired participants. | Clear floor space of at least 30 inches by 48 inches in front of the phone. Hang the phone no higher than 48 inches. Evaluate the cost to provide a public phone that is hearing aid or volume controlled, equipped with TDD or compatible. | Maintenance Supervisor Quality Assurance Coordinator | 12/30/07 | Completed By 09/30/08 check for compliance. | Consultation with the HR attorney indicated that the agency occupied this building prior to the enactment of the American Disabilities Act. Therefore the agency is not responsible for compliance at this time. |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | The fire alarm is not visible. | Place a sign on wall besides the alarm. Do not cover alarm with objects such as file cabinets. | Maintenance Supervisor | 12/30/06 | Completed By 09/30/08 Check for compliance. | Moved filing cabinet away from wall. |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | There is not a minimum of 80 inches of headroom in the library due to a beam. | Evaluate the situation for corrective action. | Maintenance Supervisor | 12/30/06 | 12/30/06 | Unable to change the door-way. |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | Waiting area is not large enough for number of participants in program and with wheelchairs. | Offer alternative arrangements or accommodations while waiting to be seen. | COO | 12/30/06 | 10/31/08 Reassess this situation after 10/1/08 when the contract with Drug Court ends. | Consultation with the HR attorney indicated that the agency occupied this building prior to the enactment of the American Disabilities Act. Therefore the agency is not responsible for compliance at this time. |
| Outpatient Services 1300 NW 6th Street Gainesville, Fl 32601 | Smoking area in front of Outpatient Services front door. | Move to a less public location. | OS Coordinator | 2006 | 2006 | Completed |
| CDS Buildings 1300 and 1218 NW 6th Street Gainesville, Fl 32601 | Uneven parking lot | Review parking lots for depressions in the asphalt. | Maintenance Supervisor | 2007-2008 | On-going task. | Completed filled in depressions with asphalt. |
| CDS Buildings 1300 and 1218 NW 6th Street Gainesville, Fl 32601 | Old wooden walk ways maybe a hazard for possible slip and fall. Debris on side walk | Replace wooden walk ways with concrete. Power wash side walk. | Maintenance Supervisor | 2007-2008 | Completed | Replaced the wood walk way with concrete. Power wash side walk. |
| CDS Buildings 1300 and 1218 NW 6th Street Gainesville, Fl 32601 | Large roots above ground may result in a falls. | Remove roots from building to parked cars. | Maintenance Supervisor | 2007-2008 | Completed | 1218 roots were removed from parking area and limerock installed. 1300 removed roots from walking paths. |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Administration 1218 NW 6th Street Gainesville, Fl 32601 | Non-Compliant with the Architectural and Physical Barriers Checklist. | Administration will provide access to the 1300 NW 6th Street, or the 3615 SW 13th Street Building and provide reasonable accommodations for any handicapped visitor, applicant, employee, participant or guest needing access to the 1218 Building. | Regional Program Coordinator/COO | On-going 12/30/06 |  | Consultation with the HR attorney indicated that the agency occupied this building prior to the enactment of the American Disabilities Act. Therefore the agency is not responsible for compliance at this time. |
| Administration 1218 NW 6th Street Gainesville, Fl 32601 | Assess stairway security. | Secure stairway if needed. | COO/Maintenance Supervisor | 08/08 | Complete | Stairway is safer. |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Interface Youth Program NW 1884 SW Grandview St. Lake City, Fl 32025 | Missing signage for accessible parking space. | Add the van sign to the handicap sign in front of the building | Maintenance Supervisor | Recheck 9/30/08 |  |  |  |
| Interface Youth Program NW 1884 SW Grandview St. Lake City, Fl 32025 | Uneven slope going from parking lot to curb. Appears to be made of stone and is rough. | Smooth the slope going to the curb. | Maintenance Supervisor | 09/30/08 |  |  |  |
| Interface Youth Program NW 1884 SW Grandview St. Lake City, Fl 32025 | No signage directing individuals to nearest accessible entrance. | Add signage directing individuals to the nearest accessible entrance. | Maintenance Supervisor | 09/30/08 |  |  |  |
| Interface Youth Program NW 1884 SW Grandview St. Lake City, Fl 32025 | Door handle on front door is not accessible. | Install a lever-type door handle on front door. | Maintenance Supervisor | 09/30/08 |  |  |  |
| Interface Youth Program NW 1884 SW Grandview St. Lake City, Fl 32025 | No directions to accessible public restroom or exit. | Add signage directing individuals to the nearest accessible public restrooms and exits. Signs need to be raised with Braille characters mounted 60 inches high adjacent to the latch side of the door. | Maintenance Supervisor | 09/30/08 |  |  |  |

## Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Interface Youth Program NW 1884 SW Grandview St. Lake City, Fl 32025 | No designated accessible public restroom. | Designate the bathroom in the boy’s hallway as the accessible public restroom: Glue down shower molding in bathroom. Install a lever- type door handle. Lower mirror in the boy’s hallway Bathroom down to 40 inches. Lower paper towel rack to 48 inches. | Maintenance - Supervisor | - 1/07 Recheck - 09/30/08 | - Completed |  |
| Interface Youth Program NW 1884 SW Grandview St. Lake City, Fl 32025 | No directions to accessible public restroom or exit. | Post signs on the inaccessible restrooms doors to direct individuals to an accessible restroom. | Maintenance Supervisor | 09/30/08 |  |  |

Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date |
| --- | --- | --- | --- | --- | --- |
| Interface Youth Program-Central 1400 NW 29th Road, Gainesville, Fl 32605 | Public telephone in lobby is not accessible. However, text messaging is available. | Evaluate the cost to provide a public phone that is hearing aid or volume controlled, equipped with TDD or compatible. Review annual budget for funding to replace telephone equipment. | Quality Assurance Coordinator | 09/30/08 | 07/08 Completed annual budget review. |
| Interface Youth Program-Central 1400 NW 29th Road, Gainesville, Fl 32605 | Improve the accessible parking space. | Repaint striped access aisle for the accessible parking space. Add a sign indicating van accessibility mount on the accessible parking space. | Maintenance Supervisor | 09/30/08 |  |
| Interface Youth Program-Central 1400 NW 29th Road, Gainesville, Fl 32605 | No signs directing individuals to accessible entrance. | Add signage directing individuals to the nearest accessible entrance. No accessibility to the recreation area in the backyard. | Maintenance Supervisor | 09/30/08 |  |
| Interface Youth Program-Central 1400 NW 29th Road, Gainesville, Fl 32605 | Restroom labeled as accessible is less accessible than another restroom in the boy’s living area. | Move handicap sign from the boy’s bedroom bathroom to the living room bathroom. | Maintenance Supervisor | 09/30/08 |  |

Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Interface Youth Program-Central 1400 NW 29th Road, Gainesville, Fl 32605 | Improve indoor access. | Widen dining room doorway to 36 inches. Add ramp to step from hallway into room before the dining room. See the ramp that goes from this room into the dining room as an adequate example. Reduce the size of the threshold going into Life Skills classroom. | Maintenance Supervisor | 09/30/08 |  |  |
| Interface Youth Program-Central 1400 NW 29th Road, Gainesville, Fl 32605 | Protruding objects in corridors. | Keep pathways at least 36 inches wide around protruding obstructions. Move desk near back door and file cabinet from corridors. | Regional Coordinator | 09/30/08 |  |  |
| Interface Youth Program-Central 1400 NW 29th Road, Gainesville, Fl 32605 | Assess for safety hazards. | Replace security fence, repair basketball court, partially replace roof, patch potholes, remove hazardous limbs and down tree, remove roots in parking area and fill with lime rock. | Maintenance Supervisor, Regional Coordinator | FY 2007-2008 | Completed |  |

Architectural Barriers

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Interface Youth Program- East 2919 Kennedy St. Palatka, Fl 32177 | Facility closed and re-opened in new temporary location, while renovations on Kennedy Street were completed. | Renovations meet current building standards for ADA. | COO and Regional Program Coordinator | On-going | Completed November 07 |  |

Other

| Location | Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| CDS Agency-wide | Office equipment: computers, faxes, printers, copiers, office space and work stations are generally not wheel chair accessible or easy to read for a person with low vision. | CDS would provide reasonable accommodations to provide accessibility for individuals in need of these corrections. | Data Manager and Regional/ Program Coordinator |  | On going |  |

#### Other Barriers

Goal: Additional barriers, as identified, will be addressed as needed and may include but are not limited to: safety, waiting lists, staff performance, program design, funding, technology, staffing patterns etc.

.

IDENTIFIED BARRIERS

| Barrier | Solution | Priority | Cost | Funding | Due Date | Responsible Staff | Program |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Web page needs updating. | Continue to seek out volunteers to help update the web site. |  | Staff time | CDS Annual Budget | On-going need | Administration | Resource Development |

## Attitudinal Barriers

Goal: To reduce the stigma associated with counseling services, runaway and troubled youth, mental illness and substance abuse by promoting the inclusion of participants of services within the community.

IDENTIFIED BARRIERS (Attitudinal)

| Barrier | Solution | Priority | Cost | Funding | Due Date | Responsible Staff | Program |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Assess attitudinal barriers. | Coordinators shall identify attitudinal barriers during staff retreats. |  | Reduction of direct services and billable units of services. | Program funding sources. | 10/08 | Coordinators | All CDS Programs |
| Eliminate the use of the word client in all written documents. | Continue to update agency policies and procedures and other written documents and eliminate the word client and replace with participant. |  | Staff time | Program funding | 07/08 | All staff | All CDS Programs |
| To provide presentations, events and materials that assist in the removal of attitudinal barriers. | Provide prevention and outreach activities to promote CDS new name, our mission and agency supported events that will reduce the stigma of accessing services. |  | Staff time | SAMH Prevention and Outreach CINS/FINS Outreach | 07/08 | Prevention Resource Development TANF Outreach | Prevention, Resource Development, CINS/FINS, |

#### Communication Barriers

Goal: To reduce communication barriers in the provision of services (i.e. language, format, cultural differences, and telecommunication).

IDENTIFIED BARRIERS (Communication)

| Barrier | Solution | Priority | Cost | Funding | Due Date | Responsible Staff | Program |
| --- | --- | --- | --- | --- | --- | --- | --- |
| To increase the availability of the information regarding the organization’s services, programs and outcomes to persons served, employees, and community stakeholders. | Provide an annual report to the public during the annual meeting. Help plan and staff a “Town Meeting” at least one time this year to address the PIPSA goal of addressing under age drinking. Continue to provide prevention activities to the general population. |  | Staff Time and Printing Costs. | CDS Annual Budget | 01/09 | Administration | Resource Development |
| Need a list of employees available to translate for non-English speaking participants. | Identify by site employees who can speak in other languages, including sign language. Develop a list and distribute it to EMT regarding individuals willing to be contacted should translations be needed. |  | Staff time | CDS Annual Budget | 09/08 | All Coordinators | All Programs |

###### Employment Barriers

Goal: To reduce barriers to employment to maintain a diverse workforce sensitive to the unique needs of clients and representative of the community.

IDENTIFIED BARRIERS (Employment)

| Barrier | Solution | Priority | Cost | Funding | Due Date | Responsible Staff | Program |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Reduction of State Funding due to revenue shortfall. | Increase effort to access donations, grants and foundations |  | Staff time | CDS Annual Budget | 07/08 | Administration | Resource Development |

##### Environmental Barriers

Goal: To reduce environmental barriers (anything about the setting that impedes service delivery)

IDENTIFIED BARRIERS (Environmental)

| Barrier | Solution | Priority | Cost | Funding | Due Date | Responsible Staff | Program |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Increase the evidence of decorations and materials that reflect the cultural diversity of persons served. | Conduct an assessment of our programs and facilities and place art, posters, reading and educational materials that reflect our diverse participants. |  | Staff time. | CDS Annual Budget | 09/08 | Coordinators | All |

### Financial Barriers

Goal: To reduce financial barriers for receiving services

IDENTIFIED BARRIERS (Financial)

| Barrier | Solution | Priority | Cost | Funding | Due Date | Responsible Staff | Program |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Reduction of State and Local funding for this fiscal year. | Try to maintain same level of services as of 7/1/08. Begin using fee scale and collecting fees based on the Federal Poverty Level for DFC. Provide Adult Substance Abuse Intervention Services at a cost equal to or below market value. |  | Staff Time | CDS Annual Budget | 07/08 | Coordinators | All Programs Drug Free Communities Outpatient Services. |

#### Transportation Barriers

Goal: Transportation barriers include inability to reach service locations or inability to fully participate in programming.   Transportation systems should fully accommodate any community member seeking to access services.

IDENTIFIED BARRIERS (Transportation)

| Barrier | Solution | Priority | Cost | Funding | Due Date | Responsible Staff | Program |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Increase cost of gasoline and travel expenses for shelters, counselors and participant. | Maintain level of services offered off site. Continue to monitor travel expenses. Provide services during the hours of public transportation bus routes. |  | Analyze cost to agency | CDS Annual Budget | On-going | Coordinators | All Programs |