CDS Family & Behavioral Health Services, Inc.

Accessibility Plan

Five Year Plan 2006/2011

Year Four

FY 2009/2010 Plan

Submitted to
Jim Pearce, Chief Executive Officer

On

August 03, 2009

Prepared by
Accessibility Work Group

| ## Mission: “Strengthening Communities by Building Strong Families” |  |  |
| --- | --- | --- |
|  | Geographical Area: Alachua, Baker, Bradford, Columbia, Dixie, Gilchrist, Hamilton, Lafayette, Levy, Madison, Putnam, Suwannee, Taylor and Union Counties |  |

This publication can be made available in multiple media formats upon request.

Executive Summary:

CDS is a not for profit community based agency dedicated to providing quality, affordable children and youth and behavioral health services in partnership with our communities.  CDS became incorporated March 20, 1970.  Interface Youth Shelter opened in Alachua County in 1978 as one of the first runaway shelters in the State of Florida.  CDS still remains today, a provider of specialized services and programs for truant, runaway, homeless, ungovernable and lockout/throwaway youth and their families. CDS also provides substance abuse and mental health prevention, outreach, intervention and outpatient services for youth and adults.

- CDS believes services should be readily accessible to the people we serve.

  - In order to meet the needs of our communities our residential shelter programs are accessible 24 hours a day, seven days a week.

  - Our 1-800 # is answered by residential staffs that are able to conduct an initial screenings, provide phone counseling, and make appropriate referrals for services 24 hours a day, 7 days per week.

  - Many of our programs operate outside of “normal business hours” in order to meet the needs of those persons who work or go to school.  Many of our services are school-based or site based.

  - CDS has worked diligently to ensure that service locations are within a 60-minute drive for all persons served.

- CDS believes services should be delivered in a respectful and culturally competent manner.

- CDS believes that its staff should, to the extent possible, be representative of the communities served.  CDS works diligently to provide participants access to a diverse and culturally competent staff in all of our programs.

- CDS believes that prevention and intervention services for at risk children and youth, and adults are a right, not a privilege, and those families and other individuals in need should be able to access appropriate services regardless of their ability to pay. As such, CDS has various methods to receive compensation for services:

  - Federal, State and TANF funds

  - Other grant funds

  - Sliding Fee Scale (and options to reduce fees, with supervisor’s approval)

  - Limited access to student interns

  - Targeted donations

  - Referrals to other agencies

- CDS believes that services should be delivered in an environment that meets the needs of the persons served, including:

  - ADA compliance

  - Safety and security

  - Adequate privacy

- CDS believes that its duty is to assist in removing barriers that prevent a person served from fully integrating into the community of his/her choice.  Therefore, CDS provides:

  - Outreach services and education through community programs and its web site

  - A place to host community coalition meetings and provide community education forums

This Accessibility Plan outlines the methodology by which we have identified barriers within CDS, our plans for removal of such barriers, our ongoing commitment to accessibility planning, and how we will communicate this plan to the public.

CDS is committed to providing a barrier-free environment for our participants, their families, our volunteers, staff, guests and the community. CDS has established an Accessibility Work Group (AWG) committed to accessibility planning, and will continue to work with our community partners towards a barrier-free society.

1. Aim - The aim of the Accessibility Work Group (AWG) for CDS is to provide a barrier free environment for our participants, their families, our volunteers, staff, and guests of CDS. The AWG will ensure compliance with American Disabilities Act (ADA) as a minimum standard, will publish an annual Accessibility Plan, and recommit annually to accessibility planning and to broadening our scope for the removal and prevention of barriers.

2. CDS commitment to accessibility planning - CDS provides counseling services that support participation in all areas of life for children, youth and adults with behavioral health needs. We focus on the strengths of individuals and their families at home, school, workplace, and community. We pursue research on best practices, education and advocacy, and participate in local, regional and state wide system of services. CDS is committed to providing a barrier-free environment for our participants, their families, our volunteers, staff and guests; to broadening the scope of accessibility planning; and to continue working with our community partners to achieve a barrier-free society.

3.  Description of CDS - CDS provides services to 14 counties: Alachua, Baker, Bradford, Columbia, Dixie, Gilchrist, Hamilton, Lafayette, Levy, Madison, Putnam, Suwannee, Taylor and Union counties and three judicial circuits. CDS maintains facilities in the three largest counties, with prevention, intervention and residential shelter programs in Alachua, Putnam and Columbia counties. The geographical area is mostly economically poor and rural, spanning from North Central Florida to the southern border of Georgia. CDS offers a variety of programs and services such as, but not limited, to screening, assessment and an intervention individual plan, group, family and individual counseling to meet the needs of participants in our program.

CDS was survey by the Commission on Accreditation of Rehabilitation Facilities (CARF) during FY 2008-2009 and received a three year accreditation.  CDS maintains Substance Abuse Licenses in Alachua, Putnam and Levy Counties, and Child Caring Licenses for Interface-Central, Interface-Northwest and Interface-East.    CDS has met or exceeded all performance measures in the CINS/FINS, SAMH, PFSF, Basic Center Grant, and United Way for fiscal year 2008-2009 contract. Major Funders includes: Partnership for Strong Families & Community Partnership for Children (contracted through Florida Department of Children and Families) and Circuit 3, 8 and 7 SAMH Program Offices with the Department of Children and Families, Florida Network of Youth and Family Services (funded through Florida Department of Juvenile Justice), Basic Center Grant and United Way.

The organization has an annual operating budget of approximately $4.2 million, approximately 120 full and part-time employees and is a multi-program agency administered through a central office.  CDS programs are:

Non-Residential Services:         	 Substance abuse prevention, intervention, and outpatient treatment programs for youth and adults.   Mental Health Case Managers and Outreach Services for TANF youth and adults.

Prevention Services:                  	Youth delinquency prevention and substance abuse prevention programs for youth and adults

Alpha:                                       	Prevention/Intervention Day Program.

Beta:                                        	Prevention/Intervention Day Program.

TASC:                                      	Substance abuse and mental health assessment services for youth involved with the Juvenile Justice System.

Independent Living:                   	Life skills for foster care and other eligible youth.

Interface/Family Action:             Program for runaway, truant and ungovernable youth and families in crisis.

Each of these programs has distinct goals and activities, which are consistent with the organization’s mission.  CDS administration utilizes centralized fiscal, human resources and data system to enhance program management.

4. Six Objectives for this Accessibility Plan:

- Identifies the membership of the Accessibility Work Group.

- Describes the process and methodology by which CDS will identify barriers.

- Identify the goals set by the Accessibility Work Group by fiscal year and outcome achieved.

- Identify barriers that have been successfully removed in the past year.

- Describes the barriers that are to be removed in upcoming years.

- Describes how CDS will communicate this accessibility plan to the public.

- Membership of the Accessibility Work Group - In consultation with the Board of Directors, the CDS CEO established the AWG in FY 2005/2006 and authorized the group to pursue its stated aim and objective. The CEO as coordinator of the Accessibility Work Group (AWG) appointed Peggy Vickers, Quality Assurance Coordinator as chair of the group.

Membership -The following members form the AWG steering committee:

| Member | Program Area |
| --- | --- |
| Sam Clark | Chief Operations Officer |
| Peggy Vickers | Quality Assurance Coordinator |
| Herman Miller | Maintenance Supervisor |
| Roy Erdman | Custodian |

- Barrier-Identification Methodologies- The AWG may use one or a combination of the following methods to identify, remove, and prevent barriers:

| Method | Description |
| --- | --- |
| Identified Barriers | Review and incorporate into the plan any barriers as identified by participants, their families, volunteers, staff, guests, monitoring or licensing bodies. |
| Conduct Surveys | Survey participants, their families, volunteers, staff and community partners to identify barriers and present suggestions for resolutions. |
| Conduct Focus Groups | Hold focus group sessions with staff and volunteers and with various participants to obtain their expertise. |
| Consult Community Groups and Organizations | Consult community organizations to educate the committee and staff such as the Center for Independence, Vocational Rehabilitation, University of Florida Counseling Rehabilitation Program, and Blind Services. |
| Conduct Accessibility Audit | Perform a review and audit utilizing available audit tools, such as the CARF Guide to Accessibility. |
| Consult Professional Services | Enlist professional services where appropriate, in matters such as architectural design, computers and business equipment, sensitivity training. |

- Four Goals FY 2009/2010 for Barriers and Outcome.

- Apply for available funding to renovate IYP-NW.

- Lease/Sell the 1300 Building.

- Update Accessibility Plan using the Strategic Retreat Summary completed in 03/08 and the 11/09 Strategic Plan.

- Change reporting period to fiscal year.

During FY 2008/2009 CDS held staff retreats in order to seek staff, as participant advocates assess their programs internal and external barriers.  The documentation is included in the Strategic Plan Summary 2008 and the questions were divided into the following categories:

- Architectural and Physical – All three IYP Shelter Programs and 3615 Building now meet ADA requirements.  The 1218 and 1300 buildings were constructed and occupied by the agency prior to the passage of the ADA requirements.  CDS plans to apply for available funding to renovate IYP-NW. CDS plans to lease/sell the 1300 building.

- Attitudinal – CDS continues to seek to reduce the stigma attached with persons who runaway, truant, ungovernable or locked out and/or homeless youth and persons with substance abuse and mental health problems.

- Environmental – CDS strives to create an environment where people are comfortable and feel their confidentiality is maintained.  Additional effort is needed to create environments that are reflective of the cultural customs of the participants we serve.

- Employment – CDS strives to maintain a diverse workforce sensitive to the unique needs of our participants.  CDS continues to strive towards hiring and maintaining the highest quality employees available.  The increase in Youth Care Workers hourly wage to $10.50 an hour has greatly reduced staff turn over.  Adjustments were made to the salaries of professional counseling staff has also assisted in stabilizing this workforce.  During the economic downturn, CDS has significantly reduced staff turnover.

- Financial – CDS continues to offer a number of services without charge to children and youth, however it is time to re-evaluate the agency position or practices to continue to offer services without charge for participants that are costing the agency money, such as urinalysis testing.

- Information, Communication and Technology - Some barriers were noted in how we share information with our participants, families and the community, and how we best utilize available technology to share such information.  CDS continues to struggle with name recognition.  Our name continues to be a barrier in the area of communication and recognition.

- Policy, Practice and Procedures - Improvements to our policies and practices are ongoing, to ensure they reflect the underlying values of CDS and our commitment to a Person-Centered Care Model. Person-Centered Care is a philosophy of support and an attitude that focuses on the strengths, needs, abilities and preferences of individuals that recognizes the role and support of family, and promotes individualized choices by participants and their families.

- Transportation – CDS will provide services in areas where public transportation is available and offer services in schools and at sites where our participants are available.  Shelters continue to provide transportation to and from school as needed.

d)  Barriers To Be Addressed In FY 2009/2010 - The removal of identified barriers is prioritized annually and presented to the CDS Executive Management Team for review, approval, and endorsement. The priority for removing barriers shall be determined on the basis of meeting the physical needs of our participants and the community, ensuring health and safety, and promoting barrier-free access to information. Refer to Action Plan FY 2009/2010, Barrier Identification, for a list of identified barriers, the recommended action and timeline for removal.

e)  Review and monitoring process - The AWG steering committee will commit to meeting every six months to:

- Continue to identify barriers

- Determine appropriate measures to ensure that removal of identified barriers has been achieved

- Ensure that all polices, practices, and services continue to prevent barriers

- Promote education and awareness

- Report annually to CDS Executive Management Team

- Communication of the Plan - This Plan will be posted on CDS Intranet, and is available upon request. Availability of this plan will be publicized to our participants, families, volunteers and employees in the Annual Report publications.

ACTION PLAN FY 2009/2010

The following serves as CDS Family & Behavioral Health Services, Inc.’s Accessibility Plan for  FY 2009/2010, a new five year plan will be due FY 2011-2012. The purpose of this document is to provide a means to facilitate continual quality improvement in the area of accessibility.

CDS Family & Behavioral Health Services, Inc. is committed to providing an organizational milieu that seeks to accommodate the needs of all persons served, employees, volunteers and stakeholders. Central to this commitment is the removal of architectural, attitudinal, employment, and other barriers that may impede full access to the services and programs of the organization.

This Accessibility Plan corresponds to CDS Family & Behavioral Health Services, Inc. internal evaluation of barriers through the use of facility inspections, assessments of need, and consumer, stakeholder, and employee feedback. The Accessibility Plan is reviewed and updated on an annual basis as apart of the agency’s Strategic Planning process, reviewed and endorsed by Executive Management Team and CEO.

## Architectural Barriers

Goal: To help identify and minimize any architectural/physical barriers to the site(s).

## Architectural Barriers- Bivens- 3615 SW 13th Street, Gainesville, Fl  32608

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Low visibility in the community—the public doesn’t know what we do. Bivens location is not listed in the United Way Substance Abuse Treatment list. CDS is located in the providers list but with the wrong telephone number. CDS is not listed in the current phone book. | More Public Service Announcements on TV/Radio. Update United Way Directory. Update telephone book. | Outreach/Safe Place Specialist and Regional Coordinators Outreach/Safe Place Specialist COO | At least monthly 01/10 Next book cycle. |  |  |
| Low name recognition in the community. | More Public Service Announcements on TV/Radio. Promotion of corporation identity through standardizing how we answer the phone. Develop a new corporate logo and market it. | Outreach/Safe Place Specialist and Regional Coordinators | At least monthly 1/10 |  |  |
| Participant transportation problems. | Public transportation is only available within the city limits of Gainesville in Alachua County. Staff is encouraged to do home visits if we can without incurring excessive travel costs. | Regional Coordinator and Counselors/Case Managers | 7/1/09 |  |  |
| Economic Shortages. | Charge fees for Drug Free Services. | Regional Coordinator and Drug Free Counselors/Case Managers and Data Systems Manager | 02/2010 |  |  |
| Appearance of the Bivens building needs improvement. | Relocate furnishing from 1300 Building. Paint needed areas. | Regional Coordinator and Drug Free Counselors/Case Managers | 9/09 |  |  |
| Our office’s appearance is not child/adolescent friendly. | Hang the Why-Try posters we got for free with our recent order; cost for frames would be involved. | QA Coordinator | 1/10 |  |  |
| Bivens needs more decoration and more attractive furniture. | Look into getting a better-looking desk in the office across from Interns Office. | Regional Coordinator | 8/09 |  |  |
| Counselor/Case Manager positions lost last FY has results in longer wait for Family Action services. | Recruit qualified interns from area Masters degree programs. | Regional Coordinator and Outreach/Safe Place Specialist | 7/09 |  |  |
| Need interpreting services sometimes. | Ask employees and or volunteers, who speak another language, if they are willing to provide interpretive services. | Regional Coordinator | On-going |  |  |
| There is confusion about the main entrance at the Bivens Office. | Clarify the main entrance to be used with signs. | Regional Coordinator | 11/09 |  |  |

Architectural Barriers Administration and IL Building-1218 NW 6th Street, Gainesville, Fl  32601

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Need a ramp for the front. | Reviewed the feasibility of a ramp was investigate. | COO | 7/09 |  |  |  |  |
| Safety of metal stairs in the rain. | Assess the safety of the stairs. | Maintenance Supervisor and Custodian | 7/09 |  |  |  |  |
| Needs new carpet, painting and repairs to the bathroom and fixing water leaks. | Assess cost of updating and repairing interior. | Maintenance Staff | 12/09 |  |  |  |  |

Architectural Barriers Interface Youth Program-Central, 1400 NW 29th Road, Gainesville, Fl  32605

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Leaving the facility via a car (truck, bicycle, etc) and making a left turn must be made with caution. Fast moving traffic coming from the right (limited site visibility due to curvature) creates a potentially dangerous situation. | Contact the City of Gainesville in order to post a warning sign so that traffic coming from that direction must approach the area (exiting the facility) with caution. | Regional Coordinator/ Residential Supervisor | 2/10 |  |  |
| Additional outside lighting is needed in the parking area and recreation area for the pxs, staff and visitors. | Contact the City of Gainesville for a site survey to determine the most adequate cost efficient solution. This project could involve the City of Gainesville or an outside vendor. | Regional Coordinator/ Residential Supervisor | 2/10 |  |  |
| The outside area near the entrance of the recreation area of the facility presents a potentially dangerous walking situation with the amount of tree roots and stumps. | Contacting several vendors that provided this service and obtain price quotes or utilize CDS Maintenance Department to complete this project. | Hired a contractor. Maintenance Supervisor | 07/09 |  |  |
| Signage is needed to indicate handicap parking and access to the building. To let staff and the public know it is available. | Post a sign to say handicap parking and access ramp is available and signs to indicate the locations. | Maintenance Supervisor | 8/09 | Co |  |

Architectural Barriers- Interface Youth Program NW, 1884 SW Grandview St., Lake City, Fl  32025

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person/Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Create separate bedroom areas for male and female participants by enlarging the entire shelter. | Apply for DCF Emergency Shelter grant funding to renovate the shelter. | COO/Regional Coordinator | 07/09 |  |  |
| Renovate the IYP-NW Shelter to comply with DCF and ADA standards. | Contract for services. | COO | 12/09 |  |  |

Architectural Barriers- Interface Youth Program- East, 2919 Kennedy St., Palatka, Fl  32177

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Rain pours off of the eves of the building directly in front of the entrance (East Shelter). | Assess the cost of adding an overhang in front of the entrance. | Maintenance Supervisor | 03/10 |  |  |
| The doorbell isn’t loud enough to be heard in the back of the shelter (East Shelter). | Assess the cost of replacing door bell with a louder system. | Maintenance Supervisor | 03/10 |  |  |
| The walls are very thin at the East shelter, you can hear others conversations. | Assign responsibility to individuals to create a system to their satisfaction to muffle voices. | Regional Coordinator | 03/10 |  |  |

Other Barriers

Goal: Additional barriers, as identified, will be addressed as needed and may include but are not limited to: safety, waiting lists, staff performance, program design, funding, technology, staffing patterns etc.

IDENTIFIED BARRIERS

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Web page needs updating. | Continue to seek out volunteers to help update the web site | Outreach/Safe Place Specialist | 03/10 |  |  |

## Attitudinal Barriers

Goal:  To reduce the stigma associated with counseling services, runaway and troubled youth, mental illness and substance abuse by promoting CDS Programs in the community.

IDENTIFIED BARRIERS (Attitudinal)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Provide more information regarding other CDS Programs, their services and benefits of the services to share with the public (2). | Updated CDS brochures and make them available to all CDS staff. | Outreach/Safe Place Specialist | 7/09 |  |  |
| More positive advocacy for our programs internally and externally. | Updated CDS brochures and make them available to CDS staff. | Outreach/Safe Place Specialist | 7/09 |  |  |

#### Communication Barriers

Goal: To reduce communication barriers in the provision of services (i.e. language, format, cultural differences, and telecommunication).

IDENTIFIED BARRIERS (Communication)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Need interpreting services sometimes. | Ask employees and or volunteers, who speak another language, if they are willing to provide interpretive services. | Regional Coordinator | On-going |  |  |
| Beta Program has a bad telephone in their Beta portable. | Levy County School Personnel requested to provide a new phone. | Prevention Coordinator | 08/09 |  |  |
| Making sure that appropriate staff are using the intranet. | Provide accessibility to internet/intranet. | Data Systems Manager | On-going |  |  |
| More departmental information on the intranet. | Up grade the CDS Web page to include a section of information specifically for employees. | Administration | 07/10 |  |  |
| Alpha Program needs a new printer. | Purchase a new printer. | Prevention Coordinator/COO | 01/10 |  |  |
| Beta Program needs the laptop that they were promised several years ago. | Purchased new laptops for all Beta Program. | Prevention Coordinator/COO | 01/10 |  |  |
| Having up-to- date Tech Assistance. | Hire an Information Specialist | Data Systems Manager | 07/09 |  |  |
| In IL our participants have trouble reaching us due to poor cell phone reception in many of the areas we serve. | PFSF purchase new cell phones for IL staff. | Regional Coordinator | 10/09 |  |  |
| In IL we are having problems with the Internet connection between CDS and PFSF, which greatly impedes communication with FCCs. | PFSF purchase new cell phones. | Regional Coordinator | 10/09 |  |  |
| IL – communication with FCCs regarding the movement of children impedes our access to provide services. | PFSF purchase new cell phones | Regional Coordinator | 10/09 |  |  |
| Make sure that individual plans are updated on time. | Provide a monthly report of when individual plans are due. | Data Systems Manager and staff | Monthly 07/09 |  |  |

###### Employment Barriers

Goal: To reduce barriers to employment to maintain a diverse workforce sensitive to the unique needs of clients and representative of the community.

IDENTIFIED BARRIERS (Employment)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Reduction of State Funding due to revenue shortfall. | Increase effort to access donations, grants and foundations | CEO/Board of Directors | 07/11 |  |  |
| CDS Agency-wide Office equipment: computers, faxes, printers, copiers, office space and work stations are generally not wheel chair accessible or easy to read for a person with low vision. | CDS will provide reasonable accommodations for individuals in need of these corrections. | Data Manager and Regional/ Program Coordinator | On-going |  |  |

Environmental Barriers

Goal: To reduce environmental barriers (anything about the setting that impedes service delivery)

IDENTIFIED BARRIERS (Environmental)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Increase the evidence of decorations and materials that reflect the cultural diversity of persons served. | Conduct an assessment of our programs and facilities and place art, posters, reading and educational materials that reflect our diverse participants. | Regional Program Coordinators | 05/10 |  |  |

### Financial Barriers

Goal: To reduce financial barriers for receiving services

IDENTIFIED BARRIERS (Financial)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Identify funds to replace the United Way Grant for ADI services for participants with a demonstrated need for financial assistance. | Apply for available funding, such as the Byrne Grant | COO | 06/09 |  |  |

#### Transportation Barriers

Goal: Transportation barriers include inability to reach service locations or inability to fully participate in programming.   Transportation systems should fully accommodate any community member seeking to access services.

IDENTIFIED BARRIERS (Transportation)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Increase cost of gasoline and travel expenses for shelters, counselors and participants. | Maintain level of services offered off site. Continue to monitor travel expenses. Provide services during the hours of public transportation bus routes. | Regional Coordinators, Data Systems Manager and CFO | Monthly review of Coordinators Budgets |  |  |