Accessibility Plan

Five Year Plan 2011/2016

ACTION PLAN FY 2011/2016

Status Update July 2014

The purpose of this document is to provide a means to facilitate continual quality improvement in the area of accessibility.

CDS Family & Behavioral Health Services, Inc. is committed to providing an organizational milieu that seeks to accommodate the needs of all persons served, employees, volunteers and stakeholders. Central to this commitment is the removal of architectural, attitudinal, employment, and other barriers that may impede full access to the services and programs of the organization.

This Accessibility Plan corresponds to CDS Family & Behavioral Health Services, Inc. internal evaluation of barriers through the use of facility inspections, assessments of need, and consumer, stakeholder, and employee feedback. The Accessibility Plan is reviewed and updated on an annual basis as a part of the agency’s Strategic Planning process, reviewed and endorsed by Executive Management Team and CEO.

## Architectural Barriers

Goal: To help identify and minimize any architectural/physical barriers to the site(s).

## architectural barriers - Bivens- 3615 SW 13th Street, Gainesville, Fl  32608

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Add Emergency Contact information and post sign on the front of the building. | Identify Emergency Contact for the Bivens building and post notices on the front of the building. | Maintenance Supervisor | 10/11 | 11/11 | Maintained on Suite 2 door. |
| Pavement and property has uneven surfaces that are too costly to repair that may create a hazard. | Add safety signs to the entrances to the property noting uneven surfaces are present and to proceed with care | Maintenance Supervisor | 12/11 | 1/12 |  |
| Parking area has several trees and limbs that could cause damage | Remove potentially dangerous trees and limbs | Maintenance Supervisor | 12/11 | 2/12 | This is an on-going issue. |
| Individuals walk up to Suite 2 door (which is locked since we no longer staff the desk in Suite 2) for assistance | Add signs directing individuals to Suite 4 for Counseling/Project Payback (added 11/12) | Human Resources | 1/13 | 1/13 | Signs are updated regularly due to weather exposure. Also add signs for changes to hours of operation. |

ARCHITECTURAL BARRIERS ADMINISTRATION AND IL BUILDING-1218 NW 6TH STREET, GAINESVILLE, FL  32601

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| The 1218 building could benefit from better signage for the location of the front door and directing individuals to Human Resources. | Add signs to direct individuals to appropriate locations | Maintenance Supervisor | 10/11 | 2/12 |  |
| It was noted that the 1218 Building needed deck | Assess the deck and determine the best course of action | Maintenance Supervisor | 11/11 | 11/13 |  |
| Pavement and property has uneven surfaces that are too costly to repair that may create a hazard. | Add safety signs to the entrances to the property noting uneven surfaces are present and to proceed with care | Maintenance Supervisor | 12/11 | 1/12 |  |

ARCHITECTURAL BARRIERS INTERFACE YOUTH PROGRAM-CENTRAL, 1400 NW 29TH ROAD, GAINESVILLE, FL  32605

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| A number of the signs on site are old and in need of replacement | Replace old signs | Maintenance Supervisor | 10/11 | 1/12 |  |
| Pavement and property has uneven surfaces that are too costly to repair that may create a hazard | Pavement and property has uneven surfaces that are too costly to repair that may create a hazard | Maintenance Supervisor | 12/11 |  | Improved signage, filled potholes |
| The shelter has several internal cameras that need to be upgraded to increase visibility for safety | Purchase 4 new color cameras | Residential Supervisor | 1/12 | 5/12 |  |

ARCHITECTURAL BARRIERS- INTERFACE YOUTH PROGRAM NW, 1884 SW GRANDVIEW ST., LAKE CITY, and FL 32025

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person/Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Put up privacy fencing around shelter | Contract for services. | COO/Regional Coordinator | 7/12 | 5/13 |  |

ARCHITECTURAL BARRIERS- INTERFACE YOUTH PROGRAM- EAST, 2919 KENNEDY ST., PALATKA, FL  32177

External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| The doorbell isn’t loud enough to be heard in the back of the shelter. (East Shelter). | Call an electrician | Residential Supervisor | 11/11 | 11/11 |  |
| Standing water in driveway. | Contact County | Regional Coordinator | 03/15 (updated due date) |  |  |
| Pavement and property has uneven surfaces that are too costly to repair that may create a hazard | Pavement and property has uneven surfaces that are too costly to repair that may create a hazard | Maintenance Supervisor | 03/15 (updated due date) |  | Improved signage |
| ARCHITECTURAL BARRIERS- SAMH- EAST, 310 SOUTH PALM AVENUE, SUITE 2., PALATKA, FL 32177 External Barriers/ Internal Barriers |  |  |  |  |  |
| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| Poor outside lighting at night. | Replace light bulbs | Maintenance Supervisor | 11/11 | 12/11 | Delete this entire section. SAMH contract ended 06/12 |
| Entrance light not working. | Repair | Regional Coordinator to contact Dr. Raby | 11/11 | 12/11 |  |
| Access to CDS building. | Add CDS Name to building sign on roadside. | Regional Coordinator | 3/11 | 2/12 |  |
| SAMH –E name recognition. | Advertise in Putnam County on Radio, Newspaper and Phonebook. | Outreach/Safe Place Specialist | On-going |  |  |
| Increased confidentiality is needed. | Increase confidentiality by tinting the window in the back office area | Regional Coordinator | 5/11 | 4/12 |  |

Other Barriers

Goal: Additional barriers, as identified, will be addressed as needed and may include but are not limited to: safety, waiting lists, staff performance, program design, funding, technology, staffing patterns etc.

IDENTIFIED BARRIERS

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Web page needs on-going updating. | Continue to seek out volunteers to help update and maintain the web site | Outreach/Safe Place Specialist | Annually reviewed | Ongoing |  |
| Economic Shortages. | Charge fees for Drug Free Services. Become an eligible Medicaid Provider | Regional Coordinator and Drug Free Counselors/Case Managers and Data Systems Manager | 02/12 | 9/12 | Deleted this barrier when the DFC program closed 12/12. |
| Need to expand CDS Quality Improvement Team. | Expand representation by adding supervisors, front line staff, consumers and families that will meet regularly and use a written plan to guide, track and celebrate progress made towards co-occurring capable. | QA Coordinator/ Coordinators |  |  | Not accomplished Lost QA position in early 2013 |
| Medical Manager is not designed to collect accurate data on how many individuals in the program have co-occurring issues. | Volunteer to pilot the state data system planned to integrate and report co-occurring data. | Data Manager/ COO | 7/11 |  | Deleted this barrier when the DFC program closed 12/12 |
| The agency has not identified and empowered change agents or champions to assist with the continuous quality improvement process. | CDS will research and receive training on the change agent process. | QA Coordinator |  |  | Not accomplished Lost QA position in early 2013 |
| CDS has a “no wrong door” access policies and procedures that emphasize welcoming and engaging all individuals and families with co-occurring issues from the moment of initial contact. | CDS needs to continue to train all staff on the “no wrong door” access policies and procedures with emphasize on welcoming and engaging all individuals and families with co-occurring issues from the moment of initial contact. | Regional Coordinator | 2/11 | On-going | Policy developed for use throughout the agency |
| Individuals and families should receive welcoming access to appropriate service regardless of active substance use issues (e.g., blood alcohol level, urine toxicology screen, length of sobriety, or commitment to maintain sobriety.) | Continue to train SAMH staff to work with individuals and families providing welcoming access to appropriate services regardless of active substance use issues. | Regional Coordinator |  |  | SAMH Intervention Program closed in 11/12 |
| Individuals and families receive welcoming access to appropriate service regardless of active mental health issues (e.g., active symptoms, type of psychiatric diagnosis, or type of prescribed psychiatric medications, such as anti-psychotics, stimulants, benzodiazepines, opiate maintenance, | Continue to train SAMH staff to work with individuals and families providing welcoming access to appropriate services regardless of active mental health issues. | Regional Coordinator |  |  | SAMH Intervention Program closed in 11/12 |
| Staff follow a procedure for clearly documenting positive screenings for co-occurring issues in the program data system. | Continue SAMH staff training on how to document co-occurring issues in Medical Manager, issues unresolved will be addressed during SAMH committee meeting | QA Coordinator/ Coordinators/ Data Manager |  |  | SAMH Intervention Program closed in 11/12 |
| SAMH staff requested clarity on accessing primary health care for every individual as needed. | The program will review and clarify its protocol on how to facilitate access to primary health care for every individual. | QA Coordinator/ Coordinators/COO |  |  | SAMH Intervention Program closed in 11/12 |
| For each of the co-occurring issues listed in the plan, there is an identified stage of change, stage matched interventions, and achievable steps to help the person feel and be successful. | Continued SAMH staff training on stages of change. | QA Coordinator/ Coordinators/COO |  |  | SAMH Intervention Program closed in 11/12 |
| Check SAMH program polices to verify that they state that individuals are not routinely discharged or punished for substance use, displaying mental health symptoms or having trouble following the individual plan. | Program policies will state clearly that individuals are not routinely discharged or “punished” for substance use, displaying mental health symptoms, or having trouble following an individual plan. | QA Coordinator/ COO |  |  | SAMH Intervention Program closed in 11/12 |
| Review/develop program policies and procedures to reward individuals for asking for help when they are having difficulty or beginning to relapse with any issue. | Program policies and procedures will be designed to reward individuals for asking for help when they are having difficulty or beginning to relapse with any issue. | QA Coordinator/ COO |  |  | SAMH Intervention Program closed in 11/12 |
| Integrated service plans and behavioral policies provide for positive reward for small steps of progress in addressing any problem, rather than focusing on negative consequences for “treatment failure”, “relapse”, “inappropriate behavior” or “non-compliance”. | Review/develop add to intranet integrated service plans and behavioral policies provide for positive reward for small steps of progress in addressing any problem, rather than focusing on negative consequences for “treatment failure”, “relapse”, “inappropriate behavior” or “non-compliance”. Add to SAMH record review for compliance | QA Coordinator/ SAMH Committee |  |  | SAMH Intervention Program closed in 11/12 |
| Each discharge plan for individuals and/or families with co-occurring issues provides for continuing integrated care with a clinician or team, ideally in a single setting. | Add to SAMH record review for compliance. | QA Coordinator/ SAMH Committee |  |  | SAMH Intervention Program closed in 11/12 |
| CDS does not have a designated program for clinicians to participate in on a regularly scheduled mental health and substance abuse provider interagency care coordination meeting that address the needs of individuals and/or families with complex issues. | Research the availability of an interagency care coordinator meeting in the community. Discuss the feasibility of adding the care coordination meeting of CDS population to address the needs of individuals and/or families with complex issues to the SAMH Committee meeting. | QA Coordinator/ COO |  |  | SAMH Intervention Program closed in 11/12 |

## Attitudinal Barriers

Goal:  To reduce the stigma associated with counseling services, runaway and troubled youth, mental illness and substance abuse by promoting CDS Programs in the community.

IDENTIFIED BARRIERS (Attitudinal)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Create a welcoming access to appropriate CINS/FINS programs and services regardless of gender identification. | Provide staff training on issues related to gender identity or expression. Work to identify CDS policies and procedures, records, forms that discriminate against transgender people and seek to include gender identity/expression in CDS non-discrimination policies. | QA Coordinator/CINS/FINS Counselor | 2/12 | 2/11 | Policy developed for use throughout the agency |
| Provide information, presentations, PSAs and events that assist in the removal of attitudinal barriers and information regarding CDS Programs, their services and benefits of these services to share with the public. | Provide PSAs and positive news events with our media partners. Provide a community event spotlighting positive youth behaviors. Continue to participate in local and regional events to promote our agency and services. Maintain current CDS brochures and make them available to all CDS staff. | Outreach/Safe Place Specialist, Volunteers and Committee members | Monthly PSAs Annual Spotlight on Youth Provide documented outreach events. Annual review and update 10/12 | Ongoing Ongoing Ongoing 10/12, 10/13, 10/14 |  |
| Reduce the rural population’s stigma towards social services. | Normalize SAMH services by providing public education | All staff | On-going |  | SAMH Intervention Program closed in 11/12 |
| Eliminate the use of verbal and written language that denotes negative traits or characteristics of children, youth and families or problem focused. | Conduct a staff/participant attitudinal assessment regarding language used within the treatment setting. | Staff and participants will complete an assessment regarding the language used within service provision. QA Coordinator, Coordinators, Employees and Participants. | 10/13 |  | SAMH Intervention Program closed in 11/12 |

#### Communication Barriers

Goal: To reduce communication barriers in the provision of services (i.e. language, format, cultural differences, and telecommunication).

IDENTIFIED BARRIERS (Communication)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Improve communication to the public that individuals with co-occurring issues are welcomed. | Re-write program brochures for participants welcoming individuals and families with co-occurring issues into service and offer hope for recovery. | COO, Outreach/Safe Place Specialist, Volunteers and SAMH Committee |  |  | SAMH Intervention Program closed in 11/12 |
| Identify how CDS wants to promote our name to the public. | Train staff to answer the phone to state the CDS name, staff name, May I help you? | COO, Regional Coordinators | 7/11 | 7/11 | Reviewed periodically based on telephone calls to CDS sites and feedback |
| Continue to promote CDS in public as a corporate identity. | Take advantage of PR moments to gain positive media attention. | CEO/COO, Outreach/Safe Place Specialist and Volunteers |  | Ongoing |  |
| To increase the availability of information regarding CDS services, programs, and outcomes to persons served, employees, communities and stakeholders. | Revise the annual report to include specific information regarding individual program outcomes. Seek to increase contact and use of local media to communicate specific information regarding programs and services. Develop and hold a Town Hall meeting yearly to communicate information regarding under-age drinking and to seek feedback from all attendees. | Outreach/Safe Place Specialist Outreach/Safe Place Specialist Prevention Coordinator | Annual Meeting On-going 4th Quarter | Moved Annual meeting to November in 12/13 and to a new venue Town Hall meetings are being managed by the local substance abuse coalition | See Annual Report See Coalition documentation of Town Hall Meetings held annually |
| Low visibility in the community—the public doesn’t know who we are or what we do. | Increase the number of Safe Place locations Establish and implement Quarterly plan to contact referral sources to increase utilization of shelter services | Outreach/Safe Place Specialist Regional Coordinators | Annual Quarterly | Basic Center Grant data report Some of these contacts occur annually and semi annually | Applied for and Received a Basic Center Grant for IYPE in 2013 and added another Outreach position. Also successfully competed for a new Basic Center Grant in IYPC to maintain current Outreach position |
| Not all CDS locations are properly identified in United Way I&R Directories. | Check United Way I&R directories for inclusion of CDS services. | COO/Outreach/Safe Place Specialist | Annual Updates | Annually check our United Way listings. |  |
| CDS is not listed correctly in all current phone books in the service area. | Update telephone book. | COO | Next book cycle. | 12/13 corrected | Continued monitor websites, telephone books, listings for our agency |
| Low name recognition in the community. | More Public Service Announcements on TV/Radio. Promotion of corporation identity through standardizing how we answer the phone. | Outreach/Safe Place Specialist and Regional Coordinators All staff review other sites performance regarding answering the phone and voice mail. | At least monthly Ongoing | On-going |  |
| Making sure that appropriate staff uses the intranet. | Provide accessibility to internet/intranet. To train staff to use new software and changes due to the new server. | Data Systems Manager | On-going |  | Policies were updated in 10/13 |
| Identify need for interpreting services. | Identified a single point of contact for all auxiliary aids/accessibility plans and accommodations made for persons with a disability. | Human Resources Specialist/Coordinator | Monthly Report | Annual Review by DCF |  |
| Hearing Impaired Attestation Training | Develop and provide training materials for CDS employees regarding the needs of persons who are deaf or hard of hearing and persons with disabilities, in accordance with Section 504 of the Rehabilitation Act and Title II of the ADA. | Human Resources Specialist/Data Manager/ Coordinator | 2/12 Annually thereafter for three years | 2/14 Continues to part of employee orientation |  |

###### Employment Barriers

Goal: To reduce barriers to employment to maintain a diverse workforce sensitive to the unique needs of participants and representative of the community.

IDENTIFIED BARRIERS (Employment)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Reduce barriers for attracting qualified employees by developing expanded revenue sources. | Increase effort to access donations, grants and foundations. Meet productivity standards set by EMT. | CEO/Board of Directors Coordinators. | On-going | Board Meeting Notes reviewed monthly. |  |
| Limited staff for scheduling coverage and to see walk-in. | Shared Calendaring | SAMH –East/Data Staff | 12/11 |  | SAMH Intervention Program closed in 06/12 |
| CDS Agency-wide Office equipment: computers, faxes, printers, copiers, office space and work stations are generally not wheel chair accessible or easy to read for a person with low vision. | CDS will provide reasonable accommodations for individuals in need of these corrections. | Data Manager and Regional/ Program Coordinator | On-going | Monitored by HR |  |
| There are not specific recovery-oriented co-occurring competencies for all staff included in human resource policies and job descriptions. | CDS will research specific recovery oriented co-occurring competencies and add them to job description. | QA Coordinator COO | 6/12 |  | SAMH Intervention Program closed in 11/12 |
| The program does not have a written scope of practice for co-occurring competency for all clinicians trained or licensed in only one area of service (e.g. licensed or formally trained in mental health OR substance abuse, but not both). | CDS will research and write a scope of practice for co-occurring competency for all clinicians trained or licensed in only one area of service. | QA Coordinator COO Regional Coordinator | 7/12 |  | SAMH Intervention Program closed in 11/12 |
| The program does not have a written plan for recovery-oriented co-occurring competency development (e.g., supervision, training activities, etc...) related to all staff (e.g., clinical, support, management, etc...) | CDS will develop a written plan for recovery-oriented co-occurring competency development. |  | 7/12 |  | SAMH Intervention Program closed in 11/12 |

Environmental Barriers

Goal: To reduce environmental barriers (anything about the setting that impedes service delivery)

IDENTIFIED BARRIERS (Environmental)

Agency-Wide External Barriers/ Internal Barriers below should be represented in the next fiscal year

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Increase the evidence of decorations and materials that reflect the cultural diversity of persons served. | Conduct an assessment of our programs and facilities and place art, posters, reading and educational materials that reflect our diverse participants. | Regional Program Coordinators | Annual | Ongoing | Added to Strategic Plan in 2015 |

### Financial Barriers

Goal: To reduce financial barriers for receiving services

IDENTIFIED BARRIERS (Financial)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Identify funding sources for adult substance abuse participants with a demonstrated need for financial assistance. | Apply for available funding when identified | COO/Data Manager/QA Coordinator | Deleted | 11/12 | We are no longer pursuing this type of service |
| CDS does not accept Medicaid or third party insurance and State funds are being transferred to a Managing Entity as of 12/11. | Complete the enrollment process for Medicaid Provider Eligibility. Seek Third Party Insurance Payers. Maintain active involvement with the ME. | DFC Coordinator/Regional Supervisor/Data Manager/QA Coordinator and COO CEO/COO | 03/12 01/12 Ongoing |  | Applied and received our Medicaid License, then made corporate decision to end SAMH Medicaid eligible services |
| The state has separate funding sources for SAMH services. | Advocate with Florida Alcohol and Drug Abuse Association and Florida Council to support the delivery of integrated approaches to funding. | CEO/COO | Ongoing |  | Continue active involvement on the board of FADA and Lutheran Services |

#### Transportation Barriers

Goal: Transportation barriers include inability to reach service locations or inability to fully participate in programming.   Transportation systems should fully accommodate any community member seeking to access services.

IDENTIFIED BARRIERS (Transportation)

Agency-Wide External Barriers/ Internal Barriers

| Barrier | Proposed Solution | Person Program Responsible | Due Date | Completion Date | Remarks |
| --- | --- | --- | --- | --- | --- |
| Public transportation is only available within the city limits of Gainesville in Alachua County. All other cities and counties have limited access to Medicaid transportation van, which only services persons with Medicaid. Increase cost of gasoline and travel expenses for shelters, counselors and participants. | Maintain level of services offered off site. Continue to monitor travel expenses. Provide services during the hours of public transportation bus routes. | Regional Coordinators, Data Systems Manager and CFO | Monthly review of Coordinators Budgets | On-going | 7/14 Transportation options remain limited |