CDS Family & Behavioral Health Services, Inc.

Business Performance Grid

Status Report 12/09

| Performance Goal | Objective(s) | Data Source(s) | Timeframes | Position Assigned | Report |
| --- | --- | --- | --- | --- | --- |
| - Funding development | Develop new revenue resources. | Board/EMT Meeting Notes | Monthly | CEO | Renewed the funding for IYP-C, Civil Citation, and PIPSA. Received second year Basic Center Grant funding. Emergency Shelter Grant for IYP-NW renovations and Challenge grant and Community Foundation grant for NW. Funding for Spotlight on Youth and applied for and received the Byrne Grant for SAMH-C. |
| - Operationalized the insurance endowment with the Maren Foundation. (Added 03/09) | Work with insurance company to develop an endowment for CDS. | CDS Board and EMT Meeting | 12/31/09 | CEO/COO/ Board President | This goal is almost complete. The board continues to work on this Endowment Activities. The Board President projects that the endowment will be somewhere between 3 and 4 million dollars for CDS when paid in full |
| - Board Retreat and Development. | Schedule a board retreat by January 2010. | Board Meeting Notes | Monthly | CEO | During the December Executive Board Meeting, they discussed scheduling a Board Retreat in March 2010. Rescheduled this goal to be completed by March 2010. |
| - Community partnership collaboration | Update cooperative service agreements by July, 2009. | EMT Meeting Notes, Update on Intranet | April - July, 2009 | CFO/QAC | 77 Cooperative Service Agreements were sent out the first quarter of the fiscal year. Updated cooperative service agreement list is available on the CDS intranet. |
| - Legislative advocacy by monitoring changes in state funding; developing action plans. | Maintain active involvement with FADAA, Florida Network South Eastern Network and Florida Network Boards and Legislative Representatives. | Board and EMT Meeting Notes Newsletters from organizations. | On-going | CEO/COO | Updates reflected in the EMT and Board Meeting Notes. |
| - Reduce/Manage Risk | Monitor the risk management plan and develop corrective action plan. | EMT Meeting Notes | Monthly | CEO/COO/ QAC | Continue assess risk. During the beginning of FY 2009-2010 CDS added a critique form to review incidents reported to SAMH, PFSF and CCC. |

Created:  07/08, Updated:  03/09, 12/09