CDS Family & Behavioral Health Services, Inc.

Business Performance Grid

5 Year Plan for 2010-2015

Six Month Status Report 8/10-3/11

| Performance Goal | Objective(s) | Data Source(s) | Timeframes | Position Assigned | Activity | Status Report |
| --- | --- | --- | --- | --- | --- | --- |
| Improve funding for CDS Program and Services | Maintain current revenue resources. Develop new revenue resources. | Board/EMT Meeting Notes | On-going | CEO, COO, Designee | Maintain CINS/FINS and SAMH level of funding. Renew the United Way and Basic Center Grant funding for IYP-C. Apply for Emergency Shelter and Challenge Grant for identified Shelters needs. Continue to identify funding sources for Spotlight on Youth through SOY committee. Applied for funding and/or grant to support CDS Mission. Board will develop an innovative fund raiser. | FY 2010-2011 Funding was maintained. Applied for new funding sources: Applied to the Partnership for an Independent Living Workforce Grant, how ever it was not funded. Applied for Drug Free Communities Grant to maintain PIPSA, however it was not funded. Contracted for $5,000 from the Florida Council on Compulsive Gambling. Received Emergency Shelter and Challenge Grant for IYP-NW shelter. This year received fewer dollars for the Spotlight on Youth program. The Board has developed an innovative fund raising, car raffle. |
| Be prepared to implement SAMH services funded by Health Care Reform. | Become a Medicaid provider. Develop a contract or service agreements with Provider Network, HMOs, Commercial Insurance for SAMH services... Develop infrastructure to provide funded services. | Board and EMT meeting notes. | 2010-2014 | CEO and EMT | Medicaid Application Process Contract with Magellan and Value Options. Complete administrative tasks from determining eligibility, co-payment, fee collection, credentialing of staff, billing (clean invoicing), payment, denial and appeal process. Improve treatment environment. Quality improvement of clinical services by- recruiting and maintain licensed people, staff training, consumer oriented services. Be able to be fully co-occurring enhanced services. | Medicaid Application is in review status. Individual licensed staffs have received a Medicaid number. CDS has a contract with Magellan only. Key staff attended the FADAA Boot Camp Series to assist the agency in preparation for Health Care Reform. The agency has a plan to be able to offer fully co-occurring. Changes include updating contract with the Alachua County Health Department which identifies a specific physician for CDS. Clinical Training was provided for all counselors/case managers in 2/11. All SAMH program completed Compass-EZ in 3/11 and all SAMH counselors/case managers are completing the CODECAT in April. The agency completed the Trauma Informed Care survey in 3/11. |
| Operationalize the insurance endowment with the Maren Foundation. (Added 03/09) | Continue to work with insurance company on the endowment for CDS. | CDS Board and EMT Meeting | On-going | CEO, COO, Board President | Continue to monitor the implementation of this endowment for CDS. Next Step is to set up a method to tract group overtime and polices related to use of endowment funds. (Added 3/11) | Life insurance policies have been issued for seven board members and seven staff. The endowment will generate 6 + million over the group morality. |
| Board Retreat and Development. | Schedule a board retreat every two years. | Board Meeting Notes | 2010 2012 2014 | CEO | During the Executive Board Meeting, discuss scheduling a Board Retreat during calendar years 2010, 2012 and 2014. | Board Retreat was held in 2010. Report of event can be located under Strategic Plan Board Retreat. |
| Increase community partnership collaboration | Update cooperative service agreements by July, 2011. July, 2013, July, 2015 | EMT Meeting Notes, Update on Intranet | April – July for 2011, 2013, 2015 | CEO, COO, Designee | Cooperative Service Agreements will be sent out the first quarter of each fiscal year every other year. Updated cooperative service agreement list shall be maintained on the CDS intranet. Increase Community Service Agreement, Partnerships, and contracts by targeting Commercial Funded Insurance Companies and Provider Networks. Increase outreach services to new referral sources with AMA, hospitals, Child Welfare, Workforce and other identified groups. |  |
| Legislative advocacy by monitoring changes in state funding; developing action plans. | Maintain active involvement with FADAA, Florida Network South Eastern Network and Florida Network Boards and Legislative Representatives. | Board and EMT Meeting Notes Newsletters from organizations. | On-going | CEO/COO | Updates reflected in the EMT and Board Meeting Notes. CEO is an active member on Florida Network Legislative and Other Committees, Also a member of the SEN Board. COO is a member of the FADAA Board. | CEO/COO continues their advocacy role. |
| Reduce and/or Manage Risk | Monitor the risk management plan and develop corrective action plan. | EMT Meeting Notes | Monthly | CEO, COO, QAC | Continue assess risk. | Recently evaluated and updated our insurance. |