CDS Family & Behavioral Health Services, Inc.

Business Performance Grid

5 Year Plan for 2020-2025

Status Report 2023

| Performance Goal | Objective(s) | Data Source(s) | Time frames | Position Assigned | Activity | Status Report |
| --- | --- | --- | --- | --- | --- | --- |
| Maintain/increase funding for CDS programs and services Maintain/increase funding for CDS program and services Maintain/increase funding for CDS programs and services Maintain/increase funding for CDS programs and services Build a new shelter in Alachua County for IYPC. | Maintain/develop revenue resources Maintain/develop revenue resources Maintain/develop revenue resources Maintain/develop revenue resources Provide a modern safe place for youth in need of shelter services | Board/EMT Meeting Minutes Board/EMT Meeting Minutes Board/EMT Meeting Minutes Board/EMT Meeting Minutes Board/EMT Meeting Minutes Board/EMT Meeting Minutes | Ongoing | CEO, COO, Designee CEO Board CEO, COO, Grant Writer CEO/COO CEO, COO, Designee CEO, Community Outreach/Safe Place Specialists CEO, Board Building Committee | Maintain/ increase CINS/FINS funding Maintain/ increase SNAP funding Hire a grant writer Create Standing Development Committee Maintain/ increase Basic Center funding Maintain/ increase SAMH funding Maintain/ increase Independent Living funding Maintain/ increase involvement with Children’s Trust, United Ways, Community Foundation, and other relevant organizations; apply for institutional and private funding as appropriate opportunities emerge. Construct new 20-bed shelter. | CINS/FINS funding was increased in FY 22/23 to ensure all staff were paid at least $15 per hour. However, the funding mechanism is contingent on Non-Residential meeting contractual requirements. Even if this occurs there has not been enough funding allocated to address compression (and impacts to other non-CINS/FINS program areas). The Florida Network will pursue a legislative remedy in the 23/24 session. CINS/FINS funding will be increased in FY 23/24 to ensure direct care staff will be paid at least $19 per hour, with the allocation mechanism to be determined. Funding for SNAP in Alachua County has been continuous since FY19/20 with an expansion for a SNAP in Schools program in FY20/21. CDS obtained SNAP funding in Lake City in FY 20/21 but was defunded the next year. CDS applied for SNAP funding again in Lake City in February of 2023 and has been funded effective May 2023; SNAP Lake City has begun virtual sessions. A PRN grant writer engaged. Has worked on a few projects (Independent Living – paused; BOA – unsuccessful; UWNCF – pending; FEMA EFSP – successful; Basic Center Grant – pending). No additional projects yet assigned. Committee created, Chair and members appointed. The Committee is meeting. IYPC was successfully renewed for a 3-year Basic Center Grant cycle in FY 20/21. IYPE did not receive renewal funding in FY19/20 but applied again in FY 20/21 and was successfully funded for 3 years. Both IYPC and IYPE have applied for new 3-year cycles in June 2023. CDS obtained a Partnership Prevention Grant (PPG) in FY 18/19 to support the Levy County Prevention (LCP) Coalition strategies and to expand Too Good for Drugs and Violence programs in Cedar Key and Yankeetown for 3 years. A second PPG was funded in FY 21/22 to continue services in Cedar Key and Yankeetown and further expand Too Good for Drugs and Violence to Bell and Trenton elementary schools in Gilchrist County. The funding is also being utilized to support the Prevention Strategies of the Gilchrist County Prevention (GCP) Coalition. This is a 3- year grant cycle. In FY 21/22, Lutheran Services of Florida (LSF) requested proposals for supplemental resources to serve providers CDS applied for and received funding to support the Alachua County Health Promotion and Wellness Coalition (HPW) and LCP and GCP. These activities were refunded in FY 22/23. LSF’s contract has been amended a number of times to address over-earnings. The Partnership for Strong Families decided to bid and expand IL services in January 2023 and CDS applied. Due to PFSF’s internal needs, the contract was extended through CY 23. Negotiation scheduled regarding contract status. CEO, Community Outreach Specialists participate regularly and actively with numerous partner agencies in order to learn and obtain additional resources. As noted above regarding the Grant Writer, CDS is aggressively seeking supplemental private and unrestricted funding from a variety of individual, family, corporate, foundation, and institutional sources; the intent is to ‘increase the size of the pie’. It is intended that these community outreach activities will continuously increase. The Gainesville-area specialist is resigning to obtain an out-of-state position; a replacement has been engaged. The Palatka-area specialist is retiring; engaging a new specialist will depend upon the outcome of the Basic Center Grant applications. CASF entered into a 50-year sublease with DCF, and delegated operational duties to CDS. $2.2MM awarded during FY 21/22 and 22/23 Legislative Sessions (administered by DJJ through Contract 10730 and amendments); a lobbyist was engaged with approval of outside counsel and auditors for compliance purposes. Board reserved funding and is seeking additional funding. Design/Build firm hired, contracts executed, and construction has commenced. Ceremonial ground-breaking occurred on May 10, 2023, with actual ground-breaking on June 5, 2023. . |
| Develop options for other CDS facilities and properties Develop options for other CDS facilities and properties Replace all vans | Maintain rental agreement with Granny D’s Daycare 1218 Building Explore options for the 1218 Building Explore options for Bivens Suite 7 Review the potential for selling the Bivens building and acquiring a smaller location Review the potential for selling IYPC after the new shelter becomes operational Review the prospect of retitling Lake City buildings into CASF Review options to obtain new vans | Board/EMT Meeting Minutes CEO, Board meeting Minutes CEO, Board Meeting Minutes CEO, Board Meeting Minutes | On-going FY 23/24 FY 23/24 FY 23/24 | CEO, COO, Board CEO and Board Members CEO and Board Members CEO and Board Members (including Development Committee) | Maintain positive working relationship and keep facility in good repair for licensure Review the feasibility of relocating 1218 staff to Bivens Under review Under review Under review | CASF listed the 1218 building in January 2022 with Coldwell Bankers and sold the building in April, 2022 to add to funds needed for the new shelter CASF listed the 1300 building with Coldwell Bankers in January 2022 sold the building in September 2022 to add to funds needed for the new shelter Staff from the 1300 building were relocated to Bivens December 1, 2021 Building appraisal obtained Building appraisal obtained Grants, donations (including leases) |
| Be prepared to operationalize DJJ/Florida Network , DCF/LSF Legislative Budget Requests or other new funding sources | Maintain a strong management team capable of change | CDS Board/ EMT Meeting Minutes | On-going | CEO, COO, Managers | Supporting/Advocating for Legislative Budget Requests through FL Network, LSF. Operationalize funded services in accordance with the requirements of the contracts. | The Florida Network sought and received additional funding for Agencies during the FY 22/23 (leading to $15/hour) and FY 23/24 (leading to $19/hour) Session. |
| Ensure Board diversity and Members who can actively contribute to the CDS mission | Add Members | Board Meeting Notes | On-going | CEO and Board | Add new Board members who are culturally, locationally, and professionally diverse and relevant to our population served and ready to contribute their expertise. | In 2022 and 2023, new members of the Board of Directors include Black males, Black females, White females, Hispanic male, from multiple counties and professions. New members include individuals with expertise in employee engagement,media, systems of care, and community development. |
| Recruit and hire qualified individuals for management positions | Identify retirement plans for key managers Plan for overlap between exiting and incoming managers for training purposes. Improve employee benefits. | EMT Minutes | On-going | CEO/COO | Advertise, recruit, interview hire and train qualified candidate’s as needed | Tracey Ousley was hired as the Interim CEO November 22, 2021 pending her retirement planned for June 30, 2023 after 25+years of service. She was replaced as the Chief Operations Officer Cindy Starling-Hersey effective February 1, 2022. Cassandra McCray retired from her positon as a Regional Director at IYPC after 37 years of service in 2022. She has been replaced with internal candidate Zeke Whitter . Gwen Love will retire as Prevention Director in June of 2023 after 39 years of service. Her replacement is Latisha Geiger (Alachua County), Jonathan Lewis (Levy, Gilchrist Counties. CDS hired Olga Rivera, CPA, as a new Comptroller in May 2023, with the position recharacterized as CFO. |
| Hire a new CEO | Establish a search committee | Board Meeting Minutes | September 2021 | Board of Directors Search Committee/Board s | Identify qualified candidate’s through screening criteria and interview Interview top candidates in person Select new CEO | Philip Kabler, J.D. was hired As CEO in March 2022. |
| Increase the visibility of CDS in the community | Rebrand CDS with a new logo and mission statement | Board/EMT Meeting Minutes | February 2023 | Board Committee, CEO, COO, and Community Outreach/Safe Place Specialist | Launch these changes through an Open House and begin changing presentations and documents accordingly | The Open House was held at Bivens in February 2023 Approximately 40 people were in attendance. The rebrand has been followed in media opportunities, social media. |
| Ensure that CDS has the best available business partners available for CPA/audit and insurance purposes | Bid CPA/audit Services Negotiate insurance agent services | CEO/Board Meeting Minutes | March 2023 | CEO,and Board of Directors | Bids were sent out on March 13,2023 requesting a response by March 31, 2023 | Thomas & Company, C.P.A., P.A. engaged for CPA/audit purposes. Brown & Brown retained for insurance agent purposes. The ERC Guy retained for ERTC application. Emerson Appraisal engaged for real property appraisal. Bruce Brashear, Esq. was engaged for a specific legal opinion. |
|  | Maintain competent legal counsel for Human Resources | CEO/HR Manager | Ongoing | CEO/HR Manager | Maintain contract with the Krizner Group | CDS consults with the Krizner Group on an as- needed basis |
| Ensure CDS/CASF bylaws are written in a manner that will properly serve the organizations Create privacy and increase accessibility to the CDS intranet | CEO draft changes for Board consideration Remove the CDS Intranet from the Public Domain Transition the intranet content to a platform which will have enhanced accessibility, ease-of-use, and sustainability | Board Meeting Minutes EMT Minutes | FY 23/24 FY 23/24 | CEO, Board of Directors (Committee) COO, Data Systems staff and CDS Admin. Consultants | CEO will research and propose changes Share Point will replace Dreamweaver to host the Intranet | Being developed by Data Systems Manager |
| Balance the expectations of the person served with the expectations of the stakeholders | Complete participant satisfaction surveys in accordance to our policies. Send out cooperative service agreements/ and satisfaction surveys, to stake holders, employee and business partners surveys annually | EMT, Director’s Meeting Notes, update on Intranet | Ongoing | CEO, COO | Participant Satisfaction Surveys will be sent out in accordance to program policies. Stakeholders, business partners and employee feedback will be completed every other year. Cooperative Agreements will be sent out the fourth quarter of each fiscal year every other year. Updated cooperative service agreement list shall be maintained on the CDS intranet. | Surveys were sent out and results reviewed by Management Cooperative Service Agreements were sent out and renewed. Surveys and Cooperative Agreements will be sent out and results will be compiled and analyzed |
| Legislative advocacy by monitoring changes in state funding; developing action plans. | Maintain active involvement with FADAA, Florida Network, LSF, and Florida Juvenile Justice Association, National Safe Place and Legislative Delegation | Board/and EMT Meeting Minutes Communications with partner organizations | On-going | CEO/COO | Updates reflected in the EMT and Board Meeting Minutes. CEO is an active member on Florida Network, FJJA,. | CEO and Board cultivates ongoing relations with Legislative Delegation, Chambers Of Commerce, Bar Associations, other organizations. |
| Reduce and manage risk | Proactively monitor the risk management plan and develop corrective action plans as-needed. | EMT Meeting Minutes | On-going | CEO, COO, Regional Directors | Continue assessing risks | Coordinate with insurance companies |