CDS Family & Behavioral Health Services, Inc.

Information Technology Five Year Plan

FY 18-19 through FY 22-23

REPORT:  June 2021

Submitted to
Jim Pearce
Chief Executive Officer

Prepared by
Information Technology Team:

Liz Tschumy	Tracey Ousley	Zach Toundas
	Data Systems Manager	Chief Operations Officer	Systems Administrator

This publication can be made available in multiple media formats upon request.

June 2021 STATUS REPORT

Information Technology Five Year Plan:  FY 18-19 through FY 22-23

## In early 2020 the COVID 19 Pandemic caught the world by surprise and required many changes in response by individuals and organizations.  In an effort to reduce human contact, CDS acquired several internet and email subscriptions described below:

## E-signatures via Hellosign allows for legally binding digital signatures from any device with internet connectivity.   It enables templates to be used as forms with efficient autofill features thus reducing the need for in office visits for guardians and staff to complete required signatures. This system also enhances interdepartmental communications securely in processing purchase orders, timesheets etc.  Implementation began in May 2020.

## Video conferencing via Zoom on its secure platform is used for board meetings, staff meetings, counseling sessions, and interviews with participants, employees and perspective employees.

## Password management via Bit warden is utilized for saving, updating and sharing passwords securely between team members and departments. It enables complex auto generated passwords to be used and changed as frequently as needed, and then redistributes new passwords to the relevant employee. It also securely manages credit cards. Bit warden is currently used by administration and fiscal and plans are moving forward to expand it agency-wide by January, 2022.

## The Systems Administrator has begun designing quick response protocols for common problems that occur in our technology systems to allow the Data Systems Manager or designee to review the symptoms’ of a specific problem and based on those symptoms’ address a fix directly as opposed to trial and error.  PowerShell Scripting software allows CDS to create coding language specifically addressing our infrastructure problems.

In July of 2021 the Data Systems Manager will begin creating form-fillable pdf documents that pre-homogenize the data to greatly increase the transferal of data from the forms to the CDS database. The focus will be on forms used most often by staff and forms that are the most commonly needed for data extraction for other reporting purposes.

MDM (Mobile Device Management) implementation for company cell phones (iPhones and Androids) is also planned to be implemented in the first Quarter of Fiscal Yr. 2021/2022. Replacement devices will be issued with MDM applications as well. MDM (Mobile Device Management) allows for remote management of cell phones, regardless of individual employee’s phone passwords and logged-in accounts. This allows us quicker recovery if lost and a faster transition when a device is passed from a departing employee to a new hire, among other benefits.

Information Technology Five Year Plan:  FY 18-19 through FY 22-23

## Categorically

| Category | Objectives | Responsibility | Implementation Schedule | Comments |
| --- | --- | --- | --- | --- |
| Hardware | - Evaluate need for replacement and upgrades of IT resources. | COO,, DSM, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Evaluate useful life of critical servers and replace as needed. | Systems Administrator | Apr. – Jun. 2021 |  |
|  | - Add backup domain controller server | COO, DSM | Completed January 2020 | Plans are in place to relocate the backup domain control server to Bivens by December 2021 |
|  | - Replace outdated desktops, laptops, and other IT equipment. | DSM, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Replace Video Surveillance Equipment in the residential shelters. | COO, Coordinators | April 2018 |  |
|  | - Conduct periodic maintenance on all equipment. | Systems Administrator | On-going |  |
|  | - Maintain an up-to-date hardware inventory system. | Systems Administrator | On-going |  |
|  | - Review and update hardware policies on an annual basis and as needed. | COO, DSM Systems Administrator | Annually: Oct. – Dec. and as needed |  |
|  | - Upgrade network hardware | COO, DSM Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Replace phone system | COO, DSM Systems Administrator | Completed May – August. 2020 | Voice Over Internet Protocol) phone cloud hosted system has resulted in increased security and economic savings |
|  | - Finalize configuration of desk phones | DSM Systems Administrator | Complete by November 2021 |  |
|  | - Implement MDM (Mobile Device Management) for company cell phones (iPhones and Androids) | DSM Systems Administrator | Complete by December 2021 |  |
| Software | - Budget for replacement, upgrades and subscriptions for software. | COO, Comptroller, DSM Systems Administrator | Annually: Jul. – Sep. |  |
|  | - Evaluate useful life of critical software on an annual basis, and replace as needed. | DSM, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Conduct periodic updates on all software. | Systems Administrator | On-going |  |
|  | - Schedule and implement all necessary training for personnel who access online systems | DSM | On-going |  |
|  | - Maintain an up-to-date software inventory system. | Systems Administrator | On-going |  |
|  | - Review and update software policies on an annual basis, or as needed. | COO, DSM Systems Administrator | Annually: Oct. – Dec. and as needed |  |
|  | - Expand use of SharePoint across programs for improved team access to share documents and to enhance collaboration. | DSM, Systems Administrator | June, 2021 thru January, 2022 |  |
|  | - Stay abreast of changes associated with external data systems and ensure that we effectively incorporate any updates into our data collection, entry and management processes. | DSM | Ongoing |  |
| Assistive Technologies | - Remain informed of changes in the requirements of title III of the Americans with Disabilities Act. | COO, DSM, Systems Administrator | On-going and Annually: Apr. – Jun. |  |
| Network Infrastructure | - Evaluate the efficacy of network infrastructure and communications providers. | DSM Systems Administrator | Annually: Jan. – Mar. |  |
|  | - Identify and implement a connectivity failover | Systems Administrator | Completed January- March 2020 |  |
|  | - Review and update network policies on an annual basis, or as needed. | COO, DSM Systems Administrator | Annually: Oct. – Dec. and as needed |  |
| Internet & E-Mail | - Evaluate the adequacy ISP providers. | COO, DSM, Systems Administrator | Annually: Jan. – Mar. |  |
|  | - Review and update internet and e-mail policies on an annual basis, or as needed. | COO, DSM | Annually: Oct. – Dec. and as needed |  |
| Websites | - Maintain CDS domain registration. | Systems Administrator | Ongoing |  |
|  | - Maintain websites’ contents to be current. | COO, Outreach Specialist | On-going |  |
|  | - Communicate website changes with personnel. | EMT | On-going |  |
|  | - Review and update website policies on an annual basis, or as needed. | COO, DSM | Annually: Oct. – Dec. and as needed |  |
|  | - Limit access to CDS intranet to CDS staff and other approved users. | COO, DSM, Systems Administrator |  | Under review by management and Systems Administrator |
| Security | - Evaluate the adequacy of security measures. | DSM, EMT, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Review and update security policies on an annual basis, or as needed. | COO, DSM, Systems Administrator | Annually: Oct. – Dec. and as needed |  |
|  | - Schedule and implement all necessary security training. | DSM, Data Systems Staff, HR Specialist | On-going |  |
| Virus Protection | - Evaluate software version upgrade needs on an annual basis, and replace as needed. | DSM, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Conduct timely updates on virus definitions. | Systems Administrator | Weekly |  |
|  | - Review and update virus protection policies on an annual basis, or as needed. | COO, DSM Systems Administrator | Annually: Oct. – Dec. and as needed |  |
| Confidentiality | - Review and update confidentiality policies on an annual basis, or as needed. | COO, DSM, | Annually: Oct. – Dec. and as needed |  |
| Data Backups | - Conduct daily backups on critical systems | Comptroller, DSM Systems Administrator | Daily |  |
|  | - Develop and maintain a backup schedule | Systems Administrator | On-going |  |
|  | - Review and update data backup policies on an annual basis, or as needed. | COO, DSM, Systems Administrator | Annually: Oct. – Dec. and as needed |  |
| Disaster Recovery | Refer to CDS Comprehensive Business Continuity Emergency Preparedness Plan, Phases 1-4 | COO | Annual Review | Updated June 2021 |