CDS Family & Behavioral Health Services, Inc.

Information Technology Five-Year Plan

FY 18-19 through FY 22-23

STATUS REPORT UPDATE:  November 2022

Submitted to
Philip N. Kabler
Chief Executive Officer

Prepared by
Information Technology Team:

Liz Tschumy	Cindy Starling-Hersey	Zach Toundas
	Data Systems Manager	Chief Operations Officer	Systems Administrator

This publication can be made available in multiple media formats upon request.

## Due to the COVID Pandemic and continuing concerns about human exposure, CDS acquired and is maintaining several internet and email subscriptions described below:

## E-signatures via Hellosign allows for legally binding digital signatures from any device with internet connectivity.   It enables templates to be used as forms with efficient autofill features thus reducing the need for in office visits for guardians and staff to complete required signatures. This system also enhances interdepartmental communications securely in processing purchase orders, timesheets etc.  Implementation began in May 2020 and is now complete.

## Video conferencing via Zoom on its secure platform is used as deemed beneficial for board meetings, staff meetings, counseling sessions, and interviews with participants, employees and perspective employees.

## Password management via Bit warden is utilized for saving, updating and sharing passwords securely between team members and departments. It enables complex auto generated passwords to be used and changed as frequently as needed, and then redistributes new passwords to the relevant employee. It also securely manages credit cards. Administration and fiscal currently use bit warden and the data systems team is reviewing the cost and benefit of agency-wide implementation.

The Fiscal and Data Systems Departments and the Independent Living program staff were relocated to Bivens and the 1218 building was sold. This transition has resulted in cost savings and greater connectivity and convenience for staff. The Systems Administrator was responsible for the movement and set up of all the hardware required from the 1218 location to Bivens resulting in a significant reallocation of time from other projects to facilitate this achievement.

One resulting outcome of the move was an increased effort toward a paperless environment when and wherever possible. For example, the fax machine at the 1218 location was not replaced and staff unfamiliar with digital scanning have been trained to use it as a more secure and environmentally friendly way to transmit information.

## The Systems Administrator continues to design quick response protocols for common problems that occur in our technology systems to allow the Data Systems Manager or designee to review the symptoms’ of a specific problem and based on those symptoms’ address a fix directly as opposed to trial and error. Creating Standard Operating Procedures for the integration of new systems such as security camera software for the shelters is a high priority for Fiscal Year 22/23 as well as expanding step-by-step protocols to Share Point, Account Management, Physical Networks, Phone Systems and Security.  PowerShell Scripting software allows CDS to create coding language specifically addressing our infrastructure problems.

The Data Systems Manager continues to build on work started last year, creating form-fillable pdf documents that pre-homogenize the data that facilitates the transferal of more data from the forms to the CDS database. The focus remains on forms used most often by staff and forms that are the most commonly needed for data extraction for other reporting purposes.

MDM (Mobile Device Management) implementation for company cell phones (iPhones and Androids) has been completed, allowing remote management of cell phones, regardless of individual employee’s phone passwords and logged-in accounts. This allows us quicker recovery if lost and a faster transition when a device is passed from a departing employee to a new hire, among other benefits.

Interface East is the fortunate recipient of a grant and donation that will afford them the opportunity to replace and upgrade their camera security system. The plan is for much of the purchasing and set up to be accomplished in-house by the Systems Administrator and is expected to result in considerable savings as well enhance his technical expertise to problem solve if issues should arise after implementation.

Staff involved in Outreach continue to build CDS visibility on platforms such as Facebook and Instagram. CDS Instagram use began in October of 2021 targeting our messages specifically toward youth traffic and millennials who have now become parents. CDS currently has 83 followers on Instagram.

Facebook is still a valuable way to reach out to parents and grandparents who are caregivers of children who may benefit from our services. CDS has 587 Facebook followers.

Ideally, each CDS program could have their own Facebook and Instagram sites to specifically expound on services available in their local area and deepen connections in their community. However achieving this would require a great deal of dedicated staff time with individuals skilled in managing this kind of presentation. To this end, the manager of the SNAP program had both the enthusiasm and skills to take on this program centric goal and began doing so in April 2022. To date SNAP has 94 Instagram followers and 98 Facebook followers.

The CDS website was revamped in October of this year to promote National Runaway month in November and add a Resource section.  CDS took this opportunity to enhance the site using key descriptive words and promotional material from national and our own sources. In part, our goal is to elevate CDS services to the first page of a Google search ensuring that our important resources are not overlooked by those seeking information about helping runaways and other homeless or troubled youth. CDS also uses You Tube as a tool to promote national events related to youth issues and provide information about relevant local resources

The CDS Systems Administrator works collaboratively with Outreach staff providing technical expertise and support for the informative and creative endeavors produced for the public and to ensure all the sites run smoothly and access is consistently available.

In the next year, CDS will assess our capability of making our presence on LinkedIn more robust as well as the value of continuing to use Mailchimp as an email-marketing platform.

Information Technology Five-Year Plan:  FY 18-19 through FY 22-23

## Categorically

| Category | Objectives | Responsibility | Implementation Schedule | Comments |
| --- | --- | --- | --- | --- |
| Hardware | - Evaluate need for replacement and upgrades of IT resources. | COO,, DSM, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Evaluate useful life of critical servers and replace as needed. | Systems Administrator | Apr. – Jun. 2023 | A server will need replacement in approximately one year and is being monitored accordingly |
|  | - Move backup domain controller server | COO, DSM | Completed December 2021 | The backup domain control server was moved to Bivens when the 1218 building was vacated. |
|  | - Replace outdated desktops, laptops, and other IT equipment. | DSM, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Replace Video Surveillance Equipment in the residential shelters. | COO, Regional Directors | Fiscal Year/22/23 | Small upgrades have been made in IYPC to date. A new system will be installed in IYPE in 2023 |
|  | - Conduct periodic maintenance on all equipment. | Systems Administrator | On-going |  |
|  | - Maintain an up-to-date hardware inventory system. | Systems Administrator | On-going |  |
|  | - Review and update hardware policies on an annual basis and as needed. | COO, DSM Systems Administrator | Annually: Oct. – Dec. and as needed |  |
|  | - Upgrade network hardware | COO, DSM Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Maintain MDM (Mobile Device Management) for company cell phones (iPhones and Androids) | DSM Systems Administrator | On-going |  |
| Software | - Budget for replacement, upgrades and subscriptions for software. | COO, Comptroller, DSM Systems Administrator | Annually: Jul. – Sep. |  |
|  | - Evaluate useful life of critical software on an annual basis, and replace as needed. | DSM, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Conduct periodic updates on all software. | Systems Administrator | On-going |  |
|  | - Schedule and implement all necessary training for personnel who access online systems | DSM | On-going |  |
|  | - Maintain an up-to-date software inventory system. | Systems Administrator | On-going |  |
|  | - Review and update software policies on an annual basis, or as needed. | COO, DSM Systems Administrator | Annually: Oct. – Dec. and as needed |  |
|  | - Expand use of SharePoint across programs for improved team access to share documents and to enhance collaboration. | DSM, Systems Administrator | June, 2021 thru January, 2022 | This objective has been moved forward to January of 2024 |
|  | - Stay abreast of changes associated with external data systems and ensure that we effectively incorporate any updates into our data collection, entry and management processes. | DSM | Ongoing |  |
| Assistive Technologies | - Remain informed of changes in the requirements of title III of the Americans with Disabilities Act. | COO, DSM, Systems Administrator | On-going and Annually: Apr. – Jun. |  |
| Network Infrastructure | - Evaluate the efficacy of network infrastructure and communications providers. | DSM Systems Administrator | Annually: Jan. – Mar. |  |
|  | - Review and update network policies on an annual basis, or as needed. | COO, DSM Systems Administrator | Annually: Oct. – Dec. and as needed |  |
| Internet & E-Mail | - Evaluate the adequacy ISP providers. | COO, DSM, Systems Administrator | Annually: Jan. – Mar. |  |
|  | - Consider alternatives to Mailchimp as an email marketing provider | Systems Administrator, Community Outreach/Safe Place Specialist, DSM, COO | January-June 2023 |  |
|  | - Review and update internet and e-mail policies on an annual basis, or as needed. | COO, DSM | Annually: Oct. – Dec. and as needed |  |
| Websites | - Maintain CDS domain registration. | Systems Administrator | Ongoing |  |
|  | - Maintain websites’ contents to be current. | COO, Outreach Specialist | On-going |  |
|  | - Communicate website changes with personnel. | EMT | On-going |  |
|  | - Review and update website policies on an annual basis, or as needed. | COO, DSM | Annually: Oct. – Dec. and as needed |  |
|  | - Limit access to CDS intranet to CDS staff and other approved users. | COO, DSM, Systems Administrator |  | Under review by management and Systems Administrator |
| Security | - Evaluate the adequacy of security measures. | DSM, EMT, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Review and update security policies on an annual basis, or as needed. | COO, DSM, Systems Administrator | Annually: Oct. – Dec. and as needed |  |
|  | - Schedule and implement all necessary security training. | DSM, Data Systems Staff, HR Specialist | On-going |  |
| Virus Protection | - Evaluate software version upgrade needs on an annual basis, and replace as needed. | DSM, Systems Administrator | Annually: Apr. – Jun. |  |
|  | - Conduct timely updates on virus definitions. | Systems Administrator | Weekly |  |
|  | - Review and update virus protection policies on an annual basis, or as needed. | COO, DSM Systems Administrator | Annually: Oct. – Dec. and as needed |  |
| Confidentiality | - Review and update confidentiality policies on an annual basis, or as needed. | COO, DSM, | Annually: Oct. – Dec. and as needed |  |
| Data Backups | - Conduct daily backups on critical systems | Comptroller, DSM Systems Administrator | Daily |  |
|  | - Develop and maintain a backup schedule | Systems Administrator | On-going |  |
|  | - Review and update data backup policies on an annual basis, or as needed. | COO, DSM, Systems Administrator | Annually: Oct. – Dec. and as needed |  |
| Disaster Recovery | Refer to CDS Comprehensive Business Continuity Emergency Preparedness Plan, Phases 1-4 | COO | Annual Review |  |