- CDS Family & Behavioral Health Services, Inc.

- FY 2008-2009 Performance Improvement Plan

- July, 2008 - February, 2009 Report

| Goal | Indicator/Outcome | Data Source | Program | Timing | Obtained By | Type of Measure |  |  |  | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Satisf. | Effective | Efficient | Access |  |
| Implement a revised satisfaction survey for SAMH services and Independent Living that will yield data assessable to CDS for analysis | Revise a participant satisfaction survey form to be more inclusive of targeted programs and procedures to implement it. | Respective meeting notes | Alpha/Beta, Drug Free Communities, Independent Living, Project Turnaround, SAMH- East, SAMH-Central | 10/2008 | Quality Assurance Coordinator Data Systems Manager Chief Operations Officer | X |  |  |  | Completed. Operationalized the participant satisfaction survey on 11/09 agency wide. |
| Participants satisfaction with services | 90% of average scores per question will be ‘4’ or greater. | Participant Satisfaction Survey | Alpha/Beta, Drug Free Communities, Independent Living, Project Turnaround, SAMH- East, SAMH-Central All participants served | Monthly Reports | Data Systems Manager Data collected by: Front Desk Staff; Counselor or designated staff member | X |  |  |  | DSM developed and trained staff on procedures for collecting participant satisfaction surveys. On 12/1/08 started the data collection on Participant satisfaction. Year to date 100% of average scores were per question were ‘4’ or greater. |
| Participant successful completion of services | 85% of participants will successfully complete CINS/FINS services. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Counselor/Case Manager or designated staff member |  | X |  |  | Non-Residential: 96.63 % successfully completed. Residential: 86.82% successfully completed. |
| Reduce juvenile crime for at risk youth. | 90% of youth served in CINS/FINS programs will remain crime free. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Counselors or designated staff members. |  | X |  |  | 100% of youth receiving services remained crime free. |
| Increase the percentage of children who successfully complete treatment | 74% of children discharged who successfully complete treatment with no alcohol and other drug use during 30 days prior to discharge. | Medical Manager & SAMH-IS | SAMH | Monthly Reports | Data Systems Manager Data collected by: Counselors |  | X |  |  | 90% of children discharged successfully completed treatment with no alcohol and other drug use during 30 days prior to discharge. |
| Reduce the NETMIS data entry lag time to less than 10 days. | 90% of intakes will be entered within 10 days. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Designated Data Entry Staff by site. |  |  | X |  | 95 %of intakes were entered within 10 days. |
| Complete follow ups of discharged CINS/FINS participants. | Follow up will be completed on 90% of participants who are discharged from CINS/FINS programs. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Counselors or designated staff members. |  |  | X |  | Follow up was completed on 99% of participants who were discharged from CINS/FINS programs. |
| Increase SAMH performance | 95% of SAMH direct service staff shall meet or exceed their expected level of contact hours as measured on a monthly basis. | Medical Manager | SAMH | Monthly Report | Data Systems Manager SAMH direct service staff |  |  | X |  | As of 2/28/09, 60% of SAMH direct service staff met or exceeded their expected level of contact hours. |
| Increase outreach efforts to the Juvenile Justice Boards and County Councils | 100% of the Juvenile Justice Boards, County Councils and programs receiving DJJ prevention funding shall be contacted annually and advised of the CINS/FINS services and informed as to how to access these services in their community. | NETMIS | CINS/FINS | Monthly Report | Data Systems Manager Meetings attended by: Designated staff |  |  |  | X | As of 2/28/09, 57% of the Juvenile Justice Boards, County Councils and programs receiving DJJ prevention funding have been contacted and advised of the CINS/FINS services and informed as to how to access these services in their community |
| Responsive to stakeholders | 90% of stakeholders surveyed will agree or strongly agree that CDS has staffs that are accessible to their organization. | Stakeholders Surveys | All programs | Annually | Chief Operations Officer Quality Assurance Coordinator |  |  |  | X | 100% of stakeholders surveyed agreed or strongly agreed that CDS personnel are accessible to their organization. |
| Reduce costs associated with Youth Care Worker supervision of participants in the residential programs | Establish biweekly budgetary guidelines for staff coverage based on licensure requirements and historical experience and provide managers biweekly personnel expenditure reports to utilize for planning and to track progress. | Bi-weekly Youth Care Worker Payroll Analysis Report | CINS/FINS Residential | Biweekly Report | Chief Financial Officer Data Systems Manager Expenses controlled by: Coordinators |  |  | X |  | As of 2/21/09 7.4% under Youth Care Worker payroll budget. (See EMT Meeting Note) |
| Reduce and/or control programs variable costs. | Establish program budgets based on historical experience and provide managers monthly expenditure reports to utilize for planning and to track progress. | Coordinator Budget Reports | All programs | Monthly Report, one week prior to EMT | Chief Financial Officer Data Systems Manager Expenses controlled by: Coordinators |  |  | X |  | As of 3/10/09 with 68.99% of the year elapsed, we have only spent 52.44% of our operating variable budget. (See EMT Meeting Note) |