- CDS Family & Behavioral Health Services, Inc.

- Performance Improvement Plan

- July 2014 – December 2014 Report

| Goal | Indicator / Outcome | Data Source | Program | Timing | Obtained By | Type of Measure |  |  |  | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Satisf. | Effective | Efficient | Access |  |
| Participant satisfaction with services | 90% of average scores per question will be ‘3’ or greater (scale 1-4). | Participant Satisfaction Survey | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Front Desk Staff; Counselor or designated staff member | X |  |  |  | 100% of all average scores were ‘3.24’ or greater. |
| Participant successful completion of services | 85% of participants will successfully complete CINS/FINS services. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Counselor/Case Manager or designated staff member |  | X |  |  | Non-Residential: 92.61 % successfully completed. Residential: 98.56% successfully completed. |
| Reduce juvenile crime for at risk youth. | 90% of youth served in CINS/FINS programs will remain crime free while receiving services. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Counselors or designated staff members. |  | X |  |  | 100% of youth receiving services remained crime free. |
| Reduce the NETMIS data entry lag time to 3 days. | 90% of intakes will be entered within 3 days. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Designated Data Entry Staff by site. |  |  | X |  | 87.38 % of intakes were entered within 3 days. This measure continues to be a challenge because data entry staff do not work weekends and holidays. |
| Complete 30-day follow ups of discharged CINS/FINS participants. | 30-day follow up will be completed on 90% of participants who are discharged from CINS/FINS programs. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Counselors or designated staff members. |  |  | X |  | A 30-day follow up was completed on 97% of participants who were discharged from CINS/FINS programs. |
| Complete 60-day follow ups of discharged CINS/FINS participants. | 60-day follow up will be completed on 90% of participants who are discharged from CINS/FINS programs. | NETMIS | CINS/FINS | Monthly Reports | Data Systems Manager Data collected by: Counselors or designated staff members. |  |  | X |  | A 60-day follow up was completed on 82% of participants who were discharged from CINS/FINS programs. This lower than expected rate of completion is partly due to initial difficulties generating accurate reports of follow-ups due. This issue has been resolved and we expect to increase our percentage accordingly. |
| Increase SAMH performance | 95% of SAMH direct service staff shall meet at least 90% of expected level of contact hours as measured on a monthly basis (staff with CDS over 3 months). | Medical Manager | SAMH | Monthly Report | Data Systems Manager SAMH direct service staff |  |  | X |  | 100% of SAMH eligible staff met at least 95% of their expected level of contact hours. |
| Responsive to stakeholders | 90% of stakeholders surveyed will agree or strongly agree that CDS has personnel who are accessible to their organization. | Stakeholders Surveys | All programs | Annually | Chief Operations Officer Quality Assurance Coordinator |  |  |  | X | This survey will be administered later in the fiscal year. |
| Reduce costs associated with Youth Care Worker supervision of participants in the residential programs | Establish biweekly budgetary guidelines for staff coverage based on licensure requirements and historical experience and provide managers biweekly personnel expenditure reports to utilize for planning and to track progress. | Bi-weekly Youth Care Worker Payroll Analysis Report | CINS/FINS Residential | Biweekly Report | Chief Financial Officer Data Systems Manager Expenses controlled by: Coordinators |  |  | X |  | YCW payroll expenses are 8% over budget. We will evaluate our budget and expenditures to determine what adjustments need to be made. |
| Reduce and/or control programs variable costs | Establish program budgets based on historical experience and provide managers monthly expenditure reports to utilize for planning and to track progress. | Coordinator Budget Reports | All programs | Monthly Report, one week prior to EMT | Chief Financial Officer Data Systems Manager Expenses controlled by: Coordinators |  |  | X |  | Our year to date expenses are 13% under budget. |